## Export
Change Initiative ID | Project ID | Change Name | Portfolio | System developed on | SDLC? | Change SubPortfolio | Portfolio Manager | Initiative Submission Status | Last Status Date | Requestor Name | Change Sponsor | BCO | Project Manager | Action Driver | Action Driver Name | Entity | Change Description | Impacted LOBs | CIO | Funding | IT Support Needed | Initiative Type | Rough Order or Magnitude | Offshoring/ Outsourcing | Related to Internal Audit | Third Party | Materiality Financial | Materiality Regulatory & Compliance Risk | Materiality ThirdParty Dependency | Materiality Information Technology | Materiality Strategic/Business Impact | Materiality Innovation/Emerging Risk | Materiality Reputational/Customer Risk | Materiality People/Change Adoption | Materiality Customer | Materiality Reputational | Change MultiYear | Project Duration | Phase | Materiality Score | Score Rationale | Materiality Override Rationale | Change Type | Target Start Date | Target End Date | Last Close Date | Status Period Ending | Overall RAG Status | Overall RAG 1 month ago | Overall RAG 3 months ago | Full NPBA Required | Strategic Alignment | Benefit Realization | Risk Assesment Status | Last Risk Assesment Approved Date | Project Server Start Date | Project Server End Date | Project Server Last Published Date | Change Submitted On | Change Approved On | Initiative Project Type | Project Type | Risk Profile Change | Inherent Risk Rating | Overall Residual Risk Rating | Overall Residual Risk Rating Override | Overall Residual Risk Override Rationale | Budget 2026 | Active / Non Project | Execution Methodology | Executive Project | Financial KPI | Financials Commentary | Financials Path To Green | Resource KPI | Resourcing Commentary | Resourcing Path To Green | Schedule KPI | Schedule Commentary | Schedule Path To Green | Scope KPI | Scope Commentary | Scope Path To Green | Technology KPI | Technology Commentary | Technology Path To Green | Exec Summary | Reason for Red or Amber | Path To Green | Return To Green | 2026 BoW | AI Service | AI Service Implementation | PoC, Prototype or Pilot required | Implementation Model | Implementation Model Description | Domain | Mega IDs | Principal Id in Fluid
73050 | NA | 26 NORTH | BSI_Products and Investments |  |  | Products |  | Out Of Scope - Approved | 10/16/2025 04:22:31 PM | Nathalie Brandon | Ivan Howard | Cynthia Morzan | NA |  |  | BSI | 26 North is a Middle and Upper middle market focused private equity strategy led by Josh Harris. | Operations;Risk;Legal; |  |  | No | Non-IT Projects | S: < $500k |  | No | No | Low | Low | N/A | N/A | N/A | N/A | Low | N/A | Low | Low | No | 0-6 Months |  | Low | . |  | NPBA; | 09/29/2025 | 11/21/2025 |  |  |  | NA | NA | No | Profitable Growth;Must-Do; | 0 | Missing |  |  |  |  | 2025-09-29 18:48 | 2025-10-16 16:23 | N/A | NA | [5 empty] | NA | Non Active |  | NA | [19 empty] | No |  |  | No
31096 | 31096 | 360Plus Enhancements Program | BSI_Technology |  |  | IT for IT | Joshua De Leon | Approved |  | Joshua De Leon | Patricia Correa | Elizabeth Noda | Patricia Correa | None | None | BSI | The 360Plus Enhancement Program aims to support business growth by introducing advanced functionalities that empower relationship managers and financial advisors. The initiative will deliver enhanced client profiling, portfolio simulation, collaboration features, and integrated analytics, ensuring Santander’s advisory services remain competitive and client-centric. |  | Jose Oliveros |  | Yes | IT Projects | M: $500k - $2M | Yes | No | Yes | Low | Moderate | High | Moderate | Moderate | Low | Low | Very Low | Low | Low | Yes | 12+ Months | Board Approved | High | this initiative is assessed as High overall, with a High third-party driver. Financial impact is Low because the budget is within the mid-size range and not expected to threaten objectives. Third-Party Dependency is High due to significant vendor/platform reliance for delivery. Regulatory/Compliance, Information Technology and Strategic/Business Impact are Moderate because 360Plus supports advisory, client profiling, portfolio simulation and analytics capabilities with fiduciary and suitability considerations. Innovation, Reputational/Customer and People impacts remain Low to Very Low under the planned enhancement approach. |  | NPBA;Technology; (IT Change) | 1/2/2026 | 12/31/2028 |  | 01/28/2026 | Not Started | NA | NA | Yes | Profitable Growth;Transformation | 0 | Missing |  |  |  |  | 2026-01-13 | 2026-01-13 | C | C | [5 empty] | $ 0 | Non Active |  | Yes | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  |  | Yes |  |  | No |  |  | Savings and Investments
32396 | 32396 | ACCH Transfers - Tableau report | BSI_Operations |  |  | N/A | Joshua De Leon | Approved |  | Carlos de Lemos | Marcel Garcia | John Pendas | Claudia Romero |  |  | BSI | New report for ACH transaction Fraud monitoring | Operations;Risk | N/A, Non-IT project |  |  | Non-IT Projects | S: < $500k |  | No | No | Very Low | Low | Very Low | Very Low | Very Low | Very Low | Very Low | Very Low | N/A | N/A | No | 0-6 Months | Execution | Low | There is only impact on the regulatory requirements due to NACHA rules. |  | Regulatory; | 7/1/2026 | 7/31/2026 |  |  |  | NA | NA | No | Must-Do | 0 | Missing | [5 empty] | 2026-07-06 | L | L | [5 empty] | $ 0 | Active | Waterfall | No | [19 empty] | No |  |  | No |  |  | Payments |  | 32396
73033 | 3777 | Advisory Office - Brazil | BSI_Strategy |  |  | N/A | Joshua De Leon | Approved |  | Cristian Krossler | Ximena Ardila | Jose Maria Lafora | Cristian Krossler | . |  | BSI | Open an investment advisory office in Brazil to expand Santander’s unique international investment solutions to the Brazilian market. The new business unit will leverage on BSI and local private bank’s wealth management expertise and on Santander’s brand awareness in Brazil, by catering to local HNW and UHNW clients and giving them the option to book in BSI’s booking center. | CommercialREVF;HR;Finance;Technology;Operations;Risk;Legal | Jose Oliveros |  | Yes | IT Projects | S: < $500k |  | No |  | Moderate | Moderate |  |  |  |  | Moderate |  | Moderate | Moderate |  | 6-12 Months | Planning | High | N/A | BCO approved risk assessment on 12/15/2025. | NPBA;Technology; (IT Change) | 9/5/2025 | 7/31/2026 |  | 7/7/2026 | On Hold | NA | NA | Yes | Profitable Growth | 1 | Approved | 12/15/2025 | 2025-01-02 | 2026-03-27 | 2026-08-29 | 2025-09-04 | 2025-09-04 | B3P | B3P | Increase | High | Low | Moderate | N/A | $ 0 | Non Active | Waterfall | Yes | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | The Advisory Office - Brazil Project placed on hold |  |  |  | Yes |  |  | No |  |  |  |  | 31116
493 | NA | AI Investment Portfolio Simulation Challenge | BSI_Products and Investments |  |  | Investments | N/A | Saved |  | Rodrigo Puga | Manuel Perez Duro | Jacqueline Rebhuhn | NA |  |  | BSI | This use case consists of an AI-driven portfolio simulation challenge designed to allow investment teams to experiment with AI tools in a fully isolated, non-production environment. Participants will manage simulated portfolios using external platforms and AI models on standalone devices with no connection to Santander systems, infrastructure, or data, in order to build familiarity with AI-assisted investment decision-making. | CommercialREVF;Technology |  |  | No | Non-IT Projects | [12 empty] | N/A | N/A | No | 6 - 12 months |  |  |  |  | Technology; (IT Change) | 5/25/2026 | 12/31/2026 |  |  |  | NA | NA | No | Transformation | 0 | Missing | [6 empty] | N/A | NA | [5 empty] | NA | Non Active |  | NA | [19 empty] | No |  |  | No
32069 | 32069 | AI Investment Portfolio Simulation Challenge | BSI_Products and Investments |  |  | Investments | Joshua De Leon | Approved |  | Diego Perez Fleta | Manuel Perez Duro | Jacqueline Rebhuhn | Diego Perez Fleta |  |  | BSI | This use case consists of an AI-driven portfolio simulation challenge designed to allow investment teams to experiment with AI tools in a fully isolated, non-production environment. Participants will manage simulated portfolios using external platforms and AI models on standalone devices with no connection to Santander systems, infrastructure, or data, in order to build familiarity with AI-assisted investment decision-making. | CommercialREVF;Technology | N/A, Non-IT project |  |  | Non-IT Projects | S: < $500k |  | No | No | Very Low | Very Low | Very Low | Very Low | Very Low | Very Low | Very Low | Very Low | N/A | N/A | No | 6 - 12 months | Execution | Very Low | N/A |  | BusinessActivity; | 5/20/2026 | 12/31/2026 |  |  |  | NA | NA | No | Transformation | 0 | Approved | 06/03/2026 |  |  |  | 2026-05-20 | 2026-05-21 | L | L | Stable | Low | Low |  | N/A | $ 0 | Active | Waterfall | No | [19 empty] | No |  |  | No |  |  | Undefined |  | 32069
72152 | 3263 | ALCO - Security Lending | BSI_Treasury and Markets | T24 | Yes | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Ted Fernandez | Jose Maria Lafora | Marcus Medeiros Carneiro Simoes | None | None | BSI | •Implement Security Lending and Repo business in ALCO desk to improve business capabilities and optimize funding sources and returns. | Finance;Technology;Operations;Risk;Legal | Jose Oliveros |  | Yes | IT Projects | S: < $500k |  | No |  | Moderate | Low |  |  |  |  | Moderate |  | Moderate | Very Low |  | 12+ Months | Closed | High | No Challenge | BCO approved risk assessment on 09/25/2025. | NPBA;Technology; (IT Change) | 1/3/2024 | 7/22/2026 | 9/2/2026 5:36:35 PM | 6/23/2026 | Complete | NA | NA | Yes | Profitable Growth | 1 | Approved | 09/25/2025 |  |  |  | 2025-05-08 | 2025-05-22 | A | A | Increase | High | Low | Moderate | N/A | $ 0 | Non Active |  | Yes | Completed |  |  | Completed |  |  | Completed |  |  | Completed |  |  | Completed |  |  | Release R2 was deployed successfully on June 17. No other releases in scope. Project ready to be closed. |  |  |  | Yes |  |  | No | Friends and Family | Friends & Family to take place in June 2025, using Santander SA as counterparty (borrower). The service should be enabled to other counterparties (approved by the Group) if F&F is sucessful.
31896 | 31896 | Alternative Investments 2.0 | BSI_Products and Investments |  |  | Products | Joshua De Leon | Approved |  | Igor Ugarte | Bueso-Inchausti Aguirre, Alvaro | Belen Monzon | Igor Ugarte |  |  | BSI | This project aims to expand the target audience and accelerate the commercialization of alternative investment products by lowering the minimum investment threshold for regulated closed-end funds and lowering the client's AUMs requirements. The initiative strengthens client relationships through longer investment horizons and improves revenue predictability. | Risk | N/A, Non-IT project |  |  | Non-IT Projects | S: < $500k |  | No | No | Very Low | Very Low | Very Low | Very Low | Low | Very Low | Low | Very Low | Moderate | Low | No | 0-6 Months | Canceled | Low | . |  | BusinessActivity; | 2/12/2026 | 4/30/2026 |  |  |  | NA | NA | No | Profitable Growth | 0 | Missing |  |  |  |  | 2026-04-01 | 2026-04-06 | L | L | [5 empty] | $ 0 | Non Active |  | No | [19 empty] | No |  |  | No |  |  | Savings and Investments
72812 | 3625 | ALTERNATIVE INVESTMENTS 2025 | BSI_Products and Investments |  |  | Investments | Joshua De Leon | Approved |  |  | Manuel Perez Duro | Jacqueline Rebhuhn | Igor Ugarte |  |  | BSI | This global project, "Alternative Investments 2025," encompasses three key releases: Release 1: Enhancements to Alternative Investments Reporting - Client Statements This release focuses on making necessary corrections and improvements to existing client statements for various Alternative Investment products, including Evergreens and Closed-End Funds. Release 2: New Asset Allocation Structure The objective of this initiative is to realign the Asset Allocation structure with new industry standards. This includes ensuring a proper allocation to Alternative Investments and Digital Assets. Furthermore, we plan to replace the current USA and EME profiles with a Standard Private Banking Profile and an Ultra-High Net Worth Individual (UHNWI) profile. Release 3: Enhancements to Alternative Investments Reporting - Advisory Report This release focuses on making necessary corrections and improvements to existing Alternative Investments sections within the Advisory Report for various products, including Evergreens and Closed-End Funds. | Technology | Jose Oliveros |  | Yes | IT Projects | S: < $500k |  | No | No | Very Low | Very Low |  |  |  |  | Low |  | Low | Very Low |  | 6-12 Months | Closed | Moderate | The aim of this global initiative is to ensure alignment with industry standards, specifically focusing on the nominee subscription process for closed-end funds, improved reporting for alternative funds, enhance the reporting of alternative investments funds and the introduction of a new asset allocation framework that appropriately accommodates alternative investments products. | BCO approved risk assessment on 05/22/2025. | Technology; (IT Change) | 3/7/2025 | 8/31/2026 |  | 9/8/2026 | Complete | NA | NA | No | Transformation | 1 | Approved | 07/09/2025 |  |  |  | 2025-03-07 | 2025-03-18 | A | A | Stable | Moderate | Low | N/A | N/A | $ 0 | Non Active |  | No | Completed |  |  | Completed |  |  | Completed |  |  | Completed |  |  | Completed |  |  | R03: Advisory Report functioning as expected. No issues reported. |  |  |  | No |  |  | No
72774 | 3598 | Alternative Operations eWorkflow | BSI_Operations |  |  |  |  | Approved | 02/20/2025 10:29:03 AM | Joshua De Leon | Maria Teresa Del Cerro | John Pendas | NA |  |  | BSI | The purpose of this project is to digitalize the exchange of client documentation between internal teams currently being performed via e-mail. Subscription documentation for new private equity funds is requested by the commercial area to the Alternative Operations team in Investment Ops. The documentation is provided by Alt Ops and once the client completes the documentation, the commercial team returns it to Alt Ops. The same exchange of documentation also takes place for AML/KYC documentation as requested by the fund administrator. The existing process is very manual and very hard to track. Follow-ups and reminders are sent via e-mail which can flood inboxes and risk being overlooked. This process enhancement will align with BPI's strategy of process improvements and digitalization. | Technology;Operations; |  | No | Yes | IT Projects | S: < $500k | Yes | No | Yes | Low | Very Low | N/A | N/A | N/A | N/A | Low | N/A | Low | Very Low | No | 6-12 Months |  | Low | n |  | Technology; | 04/01/2024 | 03/31/2025 |  | 07/01/2025 | On Hold | NA | NA | No | Simplification; | 1 | Missing |  |  |  |  | 2025-02-19 14:59 | 2025-02-20 10:29 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | Merging project to the Appian Operations eWorkflow Bucket as this should of been a part of this project. There is no impact as this project (Alternative Operations eWorkflow) did not have funding for 2025 |  |  |  | No |  |  | No
73043 | 3782 | AMC | BSI_Products and Investments |  |  | Products | Joshua De Leon | Approved |  | Nathalie Brandon | Ricardo Garcia-Marques | Cynthia Morzan | Nathalie Brandon |  |  | BSI | Lauch of a new Product Category within Structured Products business line. Actively Managed Certificates (AMC) is an execution and wrapping solution which alleviates the operational, administrative and economic burden of running an investment strategy (Managing the full lifecycle of your investment strategy through one intuitive platform) | Technology;Operations;Risk;Legal | Jose Oliveros |  | Yes | IT Projects | S: < $500k |  | No |  | Low | Low |  |  |  |  | Moderate |  | Low | Moderate |  | 6-12 Months | Concept Development | Moderate | . |  | NPBA;Technology; (IT Change) | 9/19/2025 | 6/30/2026 |  | 9/25/2026 | Green | NA | NA | Yes | Profitable Growth | 1 | Approved | 09/29/2025 | 2026-09-15 | 2027-12-17 | 2026-09-03 | 2025-09-19 | 2025-09-19 | B3P | B3P | Stable | Moderate | Low |  | N/A | $ 0 | Active | Waterfall | No | Green |  |  | Green |  |  | Green |  |  | Green |  |  | Not Started |  |  | Onboarding of the vendor |  |  |  | Yes |  |  | No |  |  |  |  | 31117
72146 | 3272 | AML Artificial Intelligence-Machine Learning | BSI_Risk |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Maria Martinez | Jose Maria Lafora | Ana Cabezuelo | None | None | BSI | This project aims to integrate Artificial Intelligence tools for Negative Media Analysis. |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k |  | No |  | Low | Moderate |  |  |  |  | Moderate |  | Very Low | Moderate |  | 12+ Months | Board Approved | Moderate | n |  | Strategy;Technology; (IT Change) | 3/1/2024 | 12/31/2027 |  | 02/14/2025 | Not Started | NA | NA | No | Simplification;Transformation | 1 | Missing |  |  |  |  | 2025-01-27 | 2025-01-27 | B3P | B3P | [5 empty] | $ 0 | Non Active |  | No | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started | [6 empty] | Yes |  |  | No |  |  | FCC/KYC/AMC
72923 | 3763 | Appian Content Management | BSI_Marketing |  |  | Marketing | Joshua De Leon | Approved |  | Luz Medrano | Maria Gisbert | Jose Maria Lafora | Luz Medrano |  |  | BSI | To uphold brand integrity, ensure regulatory compliance, and maintain client trust, SPBI must guarantee that all marketing materials are accurate, timely, and compliant. We propose the implementation of an automated tool for the approval of marketing materials, which will help reduce risk, enhance operational efficiency, and expedite go-to-market timelines. Currently, the content created by the Products and Investments teams is reviewed and approved by Compliance and Legal, while formatting is reviewed by the Marketing team. This process is managed entirely manually via email. There is a clear need for an application that can track and store the entire process, including maintaining document versions and obtaining the necessary approvals. The technology we plan to use for this solution is APPIAN. | Technology; Legal | Jose Oliveros |  | No | IT Projects | S: < $500k |  | No |  | Very Low | Low |  |  |  |  | Low |  | Low | Low |  | 6-12 Months | Planning | Very Low | Financial Impact- Since there is no cost associated with this project, BSI deems the financial impact as very low. Customer Impact- BSI deems that there will be a small number of customers impacted. Regulatory Impact- Very low as there will be no regulatory impact Reputational Impact- BSI deems there will be very low impact. | . | Strategy;Technology; (IT Change) | 6/2/2025 | 12/19/2025 |  | 8/12/2026 | On Hold | NA | NA | No | Simplification | 1 | Approved | 03/01/2026 | 2025-01-02 | 2026-12-29 | 2026-08-29 | 2025-07-03 | 2025-07-03 | B3P | B3P | Stable | Moderate | Low | Low | N/A | $ 0 | Non Active | Waterfall | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | Project has been placed on hold as per the BSI PMO Form |  |  |  | No |  |  | No |  |  |  | 6883 | 31241
30571 | 30571 | Appian EAM | BSI_Commercial |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Miguel Orozco | Carolina Alvarez | Francesca Elejalde | None | None | BSI | Development of Family Offices & Business Introducers onboarding in Appian |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k | Yes | No | Yes | Very Low | Very Low | Very Low | Moderate | Moderate | Very Low | Very Low | Low | N/A | N/A | No | 6 - 12 months | Board Approved | Moderate | Financial Impact - The project is budgeted to spend 58,000 which is within the very low threshold. Customer Impact - There will be no customer impact as the process is for internal use only to help make an analysis. Regulatory Impact - No impact to regulators. Reputational Impact - There is no impact to customers which results in no reputational impact. |  | BusinessActivity;Technology; (IT Change) | 1/2/2026 | 12/31/2026 |  | 7/23/2026 | On Hold | NA | NA | No | Simplification;Transformation | 0 | Missing |  |  |  |  | 2026-01-08 | 2026-01-08 | B3P | B3P | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | BSI PMO Forum has the project as on hold. Portfolio manager overiding PM to align status. |  |  |  | Yes |  |  | No |  |  | Savings and Investments
72145 | 3255 | Appian Electronic Workflows Operations | BSI_Operations |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Maria Teresa Del Cerro | John Pendas | Daniel Abdelnour | None | None | BSI | This project aims at automating many manual processes which currently may be subject to regulatory reviews and recomendations. As part of the transformation and automation program, BSI is implementing different workflows in the Operation area to eliminate manual interventions, improve controls and to create a more robust and flexible processes. | Technology;Operations | Jose Oliveros |  | Yes | IT Projects | M: $500k - $2M |  | No |  | Low | Very Low |  |  |  |  | Moderate |  | Moderate | Low |  | 12+ Months | Execution | High | Financial Impact - Low Customer Impact- Moderate Regulatory Impact - Very low Reputational impact - Low | BCO approved risk assessment on 09/03/2025. | Technology; (IT Change) | 1/2/2024 | 12/31/2025 |  | 7/31/2026 | Green | NA | NA | No | Simplification;Transformation | 1 | Approved | 09/03/2025 | 2024-06-06 | 2027-10-18 | 2026-08-29 | 2025-01-16 | 2025-01-23 | B3P | B3P | Stable | High | Low |  | N/A | $ 0 | Active | Waterfall | Yes | Green |  |  | Green |  |  | Green |  |  | Green |  |  | Green |  |  | Release 1 – Wire Transfers MVP1 remains active, with work still pending on T24 integrations. Appian developers have been confirmed, will resume on the first week of August to review previous work. . Release 3 – Time Deposits remains pending PMO Forum confirmation to determine if it can be removed from hold. |  |  |  | Yes |  |  | No |  |  |  | 7677, 1937, 4569, 6772, 6773, 6907, 6432 | 31099
72159 | 3337 | Appian Evolutivos (New Workflows and Enhancements) | BSI_Commercial |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Miguel Orozco | Carolina Alvarez | Francesca Elejalde | None | None | BSI | Both, the Appian client onboarding and Appian client updates workflows replaced previous manual processes. These workflows have contributed in terms of efficiency, risk control, and traceability. Appian Onboarding was implemented in 2021 and reduced the end-to-end account openning process from +60 days to 15 days on average. Appian Updates was implemented in 2024 and reduced the enclient updates process from +180 days to 16 days on average (4Q 2024). Both workflows constantly require developments due to maintenance and enhancements purposes. |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k |  | No |  | Moderate | Low |  |  |  |  | Moderate |  | Moderate | Very Low |  | 6-12 Months | Execution | Moderate | n |  | Technology; (IT Change) | 1/1/2025 | 7/31/2025 |  | 9/22/2026 | Green | NA | NA | No | Simplification;Transformation | 1 | Approved | 05/05/2025 | 2025-01-02 | 2026-12-21 | 2026-09-24 | 2025-01-27 | 2025-01-29 | B3P | B3P | Stable | Moderate | Low |  | N/A | $ 0 | Active | Waterfall | No | Green |  |  | Green |  |  | Green |  |  | Green |  |  | Green |  |  | Gate 4 approved |  |  |  | Yes |  |  | No |  |  |  | 5750, 4569, 6727 | 31112
72160 | 3443 | Appian Integracion Docusign (onboarding-updates) | BSI_Commercial |  |  | None |  | Approved | 02/10/2025 11:14:10 AM | Joshua De Leon | Eugenio Alvarez | Maria Fernanda Lopez | NA | None | None | BSI | Enhance our current Onboarding and updates process. | Technology; |  | Yes | Yes | IT Projects | S: < $500k | No | No | Yes | Low | Low | N/A | N/A | N/A | N/A | Low | N/A | Low | Low | No | 6-12 Months |  | Low | s |  | Technology; | 03/03/2025 | 12/31/2025 |  | 05/01/2025 | On Hold | NA | NA | No | Simplification; | 1 | Missing |  |  |  |  | 2025-02-10 09:44 | 2025-02-10 11:14 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | BSI will be canceling this project outright as BSI COmmercial has depreitotized this project to repritotize a new project called CornerCard. |  |  |  | No |  |  | No
72147 | 3276 | Appian KYC 2_0 | BSI_Risk |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Maria Martinez | Jose Maria Lafora | Ana Cabezuelo | None | None | BSI | Appian KYC 2.0 - KYC digitalization across the different process impacting KYC information during the whole CLC. This digitilization will highten our regulatory controls and reduce possible issues with the current manual process. |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No No: Yes; Moderate Low: Low; Low Low: Moderate; Moderate Low: Moderate; Moderate Low: Very Low; Very Low Low: Moderate | 12+ Months | Planning | Moderate | n |  | Strategy;Technology; (IT Change) | 2/1/2024 | 12/31/2025 |  | 9/30/2026 | Green | NA | NA | No | Simplification;Transformation | 1 | Approved | 09/30/2026 | 2025-01-02 | 2027-11-22 | 2026-08-30 | 2025-01-27 | 2025-01-27 | B3P | B3P | Decrease | Low | Low | N/A | N/A | $ 0 | Active | Waterfall | No | Green |  |  | Green |  |  | Green |  |  | Green |  |  | Green |  |  | The Appian KYC 2_0 Project is on track and following the steps as defined in the project plan |  |  |  | Yes |  |  | No | Phased Implementation | Phase I: Work in parallel with: KYCs Digitalization (from different sources) & Process automation Phase II: Bankers Validation. |  |  | 31109
30580 | 30580 | Appian Marketing Global Events (Phase 2) | BSI_Marketing |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Daniela Cordero | Jose Maria Lafora | Daniela Cordero | None | None | BSI | Add and/or make improvements to the existing Appian Marketing Global Event application Functionality 1: Management of Market Heads instead of regional directors in BSISA and in BSI only EAMs and Instituional clients regions. Functionality 2: Logic for Commercial Directors of BSI, BSISA, and Middle East so that each can approve/modify candidates for their center. Functionality 4: Potential Income for Clients – Guest Creation Functionality 5: Visualization and Notification of Clients without Waiver for the Commercial Team Functionality 6: Send Field 'Relevance of Inviting the Client' to TDD Functionality 7: Changes in Client Data 'Average Business Volume' and 'Income Last Year' |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k | Yes | No | Yes | Very Low | Very Low | Very Low | Very Low | Very Low | Very Low | Very Low | Very Low | Very Low | Very Low | No | 0-6 Months | Board Approved | Very Low | this initiative is assessed as Very Low overall. The change enhances an existing Appian Marketing Global Events workflow and does not materially affect budget, regulatory obligations, vendors, IT architecture, strategic commitments, emerging technology, customers or broad change adoption. Any operational changes are expected to remain within existing processes and capacity. |  | Technology; (IT Change) | 1/1/2026 | 6/1/2026 |  | 7/27/2026 | On Hold | NA | NA | No | Simplification;Transformation | 0 | Missing |  |  |  |  | 2026-01-08 | 2026-01-09 | B3P | B3P | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | This project has been deemed on hold as a result of the July BSI PMO Forum. |  |  |  | Yes |  |  | No |  |  | Savings and Investments
72154 | 3258 | Artificial Intelligence FATCA (Gen AI) | BSI_Operations |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Maria Teresa Del Cerro | John Pendas | Victoria Fernandez | None | None | BSI | The banking industry is increasingly including new technologies to enhance operational efficiency, improve customer satisfaction and reduce costs. Gen AI offers a transformative opportunity to automate and optimize core banking processes, which allows to deliver faster and more accurate personalized services. Gen AI allows banks to streamline operations and enhance decision making capabilities | Technology;Operations | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No No: No; Moderate Low: Low; Low Low: Low; Moderate Low: Low; Moderate Low: Low; Very Low Low: Low | 6-12 Months | Concept Development | Low | n |  | Technology; (IT Change) | 7/1/2025 | 12/31/2025 |  | 7/23/2026 | On Hold | NA | NA | No | Simplification | 1 | Missing |  | 2025-01-02 | 2025-12-31 | 2026-08-30 | 2025-01-23 | 2025-01-23 | A | A | [5 empty] | $ 0 | Non Active | Waterfall | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | BSI PMO Forum has the project as on hold. Portfolio manager overiding PM to align status. |  |  |  | Yes |  |  | No |  |  |  |  | 31100
72141 | 3266 | Automated Budget Tool Vendor Selection | BSI_Finance |  |  | None |  | Approved | 01/27/2025 04:01:05 PM | Joshua De Leon | Eloina Franco-Espinosa | Jose Maria Lafora | NA | None | None | BSI | Automation of the Forecasting & Budgeting function, for the Banks Balance Sheet and Profit & Loss Statements with specific emphasis on NII, Fees & Commissions, Payroll & Benefits, Operating Expenses , Fixed Asset/Capex, and Pre-Paid Expense projections. Controlled data environment & tighten version control. 3) Bring in the actual Balance Sheet and P&L granular data | Finance;Technology; |  | Yes | Yes | IT Projects | M: $500k - $2M | No | No | Yes | Very Low | Very Low | N/A | N/A | N/A | N/A | Moderate | N/A | Moderate | Low | No | 6-12 Months |  | Moderate | No Challenge |  | Technology;BusinessActivity; | 01/01/2025 | 12/31/2025 |  | 02/14/2025 | On Hold | NA | NA | No | Simplification;Transformation; | 1 | Missing |  |  |  |  | 2025-01-16 10:42 | 2025-01-27 16:01 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | Cancelling the Project as avoid duplicating efforts by undergoing the installation of a Budgeting Tool in the Empyriam platform and then migrating to the Oracle platform, consistent with what Shusha might imple |  |  |  | No |  |  | No
72153 | 3525 | Automatic Signature Verification | BSI_Operations |  |  | None |  | Approved | 02/10/2025 12:55:02 PM | Joshua De Leon | Javier Rodriguez Hergueta | John Pendas | NA | None | None | BSI | Enhance the current verification signature process by automating certain thresholds and processes. | Technology;Operations; |  | Yes | Yes | IT Projects | M: $500k - $2M | No | No | Yes | Low | Low | N/A | N/A | N/A | N/A | Low | N/A | Low | Low | No | 6-12 Months |  | Low | s |  | Technology;BusinessActivity; | 03/03/2025 | 12/31/2025 |  | 03/11/2025 | On Hold | NA | NA | No | Simplification; | 1 | Missing |  |  |  |  | 2025-02-10 09:46 | 2025-02-10 12:55 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | This project has received excecutive sponsor approval to cancel the project as we will not go forward with it never started and resources were not engaged. |  |  |  | No |  |  | No
72164 | 3256 | Broadridge | BSI_Operations |  |  | None |  | Approved | 01/23/2025 04:06:14 PM | Joshua De Leon | Javier Rodriguez Hergueta | John Pendas | NA | None | None | BSI | Broadridge provides tax data on securities that may have payment adjustments from a tax perspective. Through the CUSIP a list can be built to track securities, their corresponding factor, and payment information. This service is needed for Tax Year 2024 for at least three years. BSI can either send CUSIP information to the Vendor and get the classification factor via email, or access a Web-based platform to research by CUSIP number. | Technology;Operations; |  | Yes | Yes | IT Projects | S: < $500k | No | No | Yes | Very Low | Very Low | N/A | N/A | N/A | N/A | Low | N/A | Low | Low | No | 6-12 Months |  | Low | No Challenge |  | Technology; | 01/01/2025 | 03/31/2025 |  | 05/07/2025 | On Hold | NA | NA | No | Simplification; | 1 | Missing |  |  |  |  | 2025-01-16 10:45 | 2025-01-23 16:06 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | The project is being cancelled because after a internal review, BSI has concluded that this is a non-IT project. BSi has reonboarded this project as a non-IT. |  |  |  | No |  |  | No
72870 | NA | Broadridge ETF | BSI_Operations |  |  |  |  | Out Of Scope - Approved | 06/05/2025 04:50:21 PM | Joshua De Leon | Javier Rodriguez Hergueta | John Pendas | NA |  |  | BSI | Broadridge provides tax data on securities that may have payment adjustments from a tax perspective. Through the CUSIP a list can be built to track securities, their corresponding factor, and payment information. This service is needed for Tax Year 2024 for at least three years. BSI can either send CUSIP information to the Vendor and get the classification factor via email, or access a Web-based platform to research by CUSIP number. | Operations; |  |  | No | Non-IT Projects | S: < $500k | Yes | No | Yes | Very Low | Very Low | N/A | N/A | N/A | N/A | Low | N/A | Low | Low | No | 6-12 Months |  | Low | We deemed the Materiality to be Low as this portal access is only to obtain public information. |  | BusinessActivity; | 02/03/2025 | 05/16/2025 |  |  |  | NA | NA | No | Simplification; | 0 | Missing |  |  |  |  | 2025-04-21 16:43 | 2025-06-05 16:50 | N/A | NA | [5 empty] | NA | Non Active |  | NA | [19 empty] | No |  |  | No
31172 | 31172 | Capial RWA Model Change | BSI_Finance |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Lina Acuna | Jose Maria Lafora | Julio Leanez | None | None | BSI | Regulatory Requirement |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No | No | Yes | Very Low | Very Low |  |  |  |  | Very Low |  | Very Low | Very Low | No | 6 - 12 months | Board Approved | Very Low | Financial Impact is set to very low as the project budget is 75k. Customer Impact very low due to not having any customers affected. Regulatory Impact- Is very low as there is no new regulation to adjust to. This project was identified as a just in case the regulation was going to change regarding RWA. Reputational Impact - as the impact for the above are very low, there is no reputational impact. |  | Technology; (IT Change) | 3/1/2026 | 9/1/2026 |  | 01/28/2026 | Not Started | NA | NA | No | Must-Do | 0 | Missing |  |  |  |  | 2026-01-14 | 2026-01-15 | B3P | B3P | [5 empty] | $ 0 | Non Active |  | No | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  |  | Yes |  |  | No |  |  | MIS (all financial and non-financial information)
72161 | 3269 | Capital RWA Model Change | BSI_Finance |  |  | None |  | Approved | 01/27/2025 03:57:17 PM | Joshua De Leon | Eloina Franco-Espinosa | Jose Maria Lafora | NA | None | None | BSI | Meet Regulatory Requirements from US and ECB Bank Regulators, which are associated with new rules to comply with Capital requirements based on Risk Weighted Assets. Would require support from Hexaware, an external Technolgy that support the RWA calculations for the Bank. This vendor / technology is currently used by the Bank for calculation of RWA Capital requirements | Finance;Technology; |  | Yes | Yes | IT Projects | S: < $500k | Yes | No | Yes | Moderate | High | N/A | N/A | N/A | N/A | High | N/A | Very Low | High | No | 6-12 Months |  | High | n |  | Technology;Regulatory; | 02/03/2025 | 12/31/2025 |  | 06/16/2025 | On Hold | NA | NA | No | Must-Do; | 1 | Missing |  |  |  |  | 2025-01-27 08:18 | 2025-01-27 15:57 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | Rationale: No increase or modification of capital requirement for the bank for 2025 so there is no need to update Risk Weight Asset model for capital calculation for BSI |  |  |  | No |  |  | No
72157 | 3213 | COE | BSI_Technology |  |  | IT for IT |  | Approved | 01/16/2025 11:48:08 AM | Joshua De Leon | Javier Rodriguez Hergueta | Elizabeth Noda | NA | None | None | BSI | Center of Excellence of BSI to provide development services in different technologies used by BSI include but not limited to T24, Appian, Web, Tableau, Oracle, SQL. Consultants will be located in different countries supporting new initiatives and/or projects. | Technology; |  | Yes | Yes | IT Projects | L: > $2M | No | No | Yes | Moderate | Very Low | N/A | N/A | N/A | N/A | Low | N/A | Low | Low | No | 6-12 Months |  | Moderate | Financial Impact- Moderate Customer Impact- Low Regulatory Impact- Very Low Reputational Impact- Low |  | Technology; | 01/01/2025 | 12/31/2025 |  | 03/12/2026 | On Hold | NA | NA | No | Simplification;Transformation; | 1 | Missing |  |  |  |  | 2025-01-16 11:45 | 2025-01-16 11:48 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | BSI is deciding to cancel this project as there was a change in strategy. No funds were allocated within 2026. |  |  |  | No |  |  | No
31881 | 31881 | Co-investment Atletico de Madrid | BSI_Products and Investments |  |  | Products | Joshua De Leon | Approved |  | Igor Ugarte | Bueso-Inchausti Aguirre, Alvaro | Belen Monzon | Igor Ugarte |  |  | BSI | The proposed co-investment will be offered with Banco Santander International investors participating in up to €50-100 million of Apollo’s total equity investment. This represents an estimated 3-6% indirect ownership in the Club, from the Apollo current stake at approximately 56.9% of the Club. | Operations;Risk;Legal | N/A, Non-IT project |  |  | Non-IT Projects | S: < $500k |  | No | No | Low | Low | Low | Very Low | Low | Very Low | Low | Very Low | Low | Low | No | 0-6 Months | Execution | Low | this initiative is assessed as Low overall. The co-investment offering creates limited Financial, Regulatory/Compliance, Third-Party, Strategic/Business and Reputational/Customer considerations due to the investment-product nature and client participation, but the project is out of scope and does not appear to require material IT, innovation or broad people/process change. Overall delivery and customer impacts are expected to be manageable. |  | NPBA; | 1/15/2026 | 2/16/2026 |  |  |  | NA | NA | Yes | Profitable Growth | 0 | Approved | 08/06/2026 |  |  |  | 2026-01-23 | 2026-01-30 | L | L | Stable | Moderate | Low |  | N/A | $ 0 | Active | Waterfall | No | [19 empty] | No |  |  | No |  |  | Savings and Investments |  | 31881
73126 | NA | Co-investment Atletico de Madrid | BSI_Products and Investments |  |  | Products |  | Submitted | 12/19/2025 04:45:05 PM | Igor Ugarte | Bueso-Inchausti Aguirre, Alvaro | Cynthia Morzan | NA |  |  | BSI | The proposed co-investment will be offered with Banco Santander International investors participating in up to €50-100 million of Apollo’s total equity investment. This represents an estimated 3-6% indirect ownership in the Club, from the Apollo current stake at approximately 56.9% of the Club. | Operations;Risk;Legal; |  |  | No | Non-IT Projects | S: < $500k |  | No | No | Low | Low | N/A | N/A | N/A | N/A | Low | N/A | Low | Low | No | 0-6 Months |  | Low | . |  | NPBA; | 01/15/2026 | 02/16/2026 |  |  |  | NA | NA | No | Profitable Growth;Must-Do; | 0 | Missing |  |  |  |  | 2025-12-19 16:45 |  | N/A | NA | [5 empty] | NA | Non Active |  | NA | [19 empty] | No |  |  | No
72026 | 3592 | Configuration Drift | BSI_Technology |  |  |  |  | Approved | 03/06/2025 03:25:17 PM | Joshua De Leon | Jose Oliveros | Elizabeth Noda | NA |  |  | BSI | This solution will reduce the technology risk of implementing changes in our current infrastructure enviroment. The Implemention of this new tool will monitor and control changes peformed in the infrastructure enviroment thus giving a more robust and secure change enviroment. | Technology;Operations; |  | No | Yes | IT Projects | S: < $500k | Yes | No | Yes | Very Low | Very Low | N/A | N/A | N/A | N/A | Very Low | N/A | Very Low | Very Low | No | 6-12 Months |  | Very Low | n |  | Technology; | 02/20/2025 | 12/31/2025 |  | 03/21/2025 | On Hold | NA | NA | No | Simplification;Transformation; | 1 | Missing |  |  |  |  | 2025-02-20 11:34 | 2025-03-06 15:25 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | Project was canceled prior to Alexandria finalization. This project was merged in Mature Infrastrusture project. |  |  |  | No |  |  | No
72748 | 3631 | CornerCard | BSI_Commercial |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Miguel Orozco | Carolina Alvarez | Jose Lafarga |  |  | BSI | Launch a Payment Card (Visa & Mastercard) with Cornercard, to serve our clients having in mind that Amex Portfolio is closing |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No: No; Low: Very Low; Low: High; Low: Low; Low: Low; Low: Low | 0-6 Months | Execution | Moderate | 1- Financial Impact- Investement is low 2- Customer Impact- Decision of the client to accept or decline. They will not be olibgated to use the Corner Card offered by Santander. Regulatory Impact- TRPM came out with a high Regulatory compliance rating. Reupational Impact- We rated as Low due to the client offshore having other ways of using there funds. Corner card will be a secondary card for the client. | BCO approved risk assessment on 09/03/2025. | NPBA;Technology; (IT Change) | 2/12/2025 | 8/31/2025 |  | 7/27/2026 | On Hold | NA | NA | Yes | Profitable Growth | 1 | Approved | 09/03/2025 | 2024-06-30 | 2026-12-31 | 2026-08-30 | 2025-02-12 | 2025-02-26 | B3P | B3P | Stable | Moderate | Low | Moderate | N/A | $ 0 | Non Active | Waterfall | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | This project has been deemed on hold as a result of the July BSI PMO Forum. |  |  |  | Yes |  |  | No |  |  |  | 7604 | 31113
31899 | 31899 | Corporate Credit Card requests workflow automation | BSI_Procurement |  |  | N/A | Joshua De Leon | Approved |  | Nadina De Castro | Nadina De Castro | Jose Maria Lafora | Nadina De Castro | NA | NA | BSI | Create workflow for approval for corporate credit applications in Service Now, replacing a form and email approval process. | Finance | N/A, Non-IT project |  |  | Non-IT Projects | S: < $500k |  | No | No | Very Low | Very Low | Very Low | Very Low | Low | Very Low | Very Low | Low | Very Low | Very Low | No | 0-6 Months | Execution | Low | this initiative is assessed as Low overall. Financial, Regulatory/Compliance, Third-Party, IT, Innovation and Reputational/Customer impacts are Very Low because the change automates an internal corporate credit-card approval workflow in ServiceNow and replaces a form/email process. Strategic/Business Impact and People/Change Adoption are Low because users will need to follow a new workflow, but the change is localized and manageable. |  | BusinessActivity; | 3/24/2026 | 6/30/2026 |  |  |  | NA | NA | No | Simplification | 0 | Missing | [5 empty] | 2026-03-16 | L | L | [5 empty] | $ 0 | Active | Waterfall | No | [19 empty] | No |  |  | No |  |  | Savings and Investments |  | 31899
72143 | 3257 | CSP Provider - FileNet | BSI_Operations |  |  | None |  | Approved | 01/23/2025 04:07:38 PM | Joshua De Leon | Javier Rodriguez Hergueta | John Pendas | NA |  |  | BSI | Replace current Content Service Provider used to archive client documentation and display shared documents between different areas of the bank. The goal is to streamline document management, regulatory compliance and increase operational efficiency | Technology;Operations; |  | Yes | Yes | IT Projects | M: $500k - $2M | No | No | Yes | Low | Moderate | N/A | N/A | N/A | N/A | Moderate | N/A | Low | Moderate | No | 12+ Months |  | Moderate | Financial Impact low, Customer impact is low, Regulastory Impact is moderate, Reputational impact is Moderate |  | Technology;Regulatory; | 01/02/2024 | 07/29/2025 |  | 06/13/2025 | On Hold | NA | NA | No | Transformation; | 1 | Missing |  |  |  |  | 2025-01-16 10:59 | 2025-01-23 16:08 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | Project will be cancelled. BSI is awaiting with new project to be loaded so that the budget can be adjusted. |  |  |  | No |  |  | No
72137 | 3277 | Data Mart | BSI_Risk |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Maria Martinez | Jose Maria Lafora | Juan Mozos Nieto | None | None | BSI | To create a Data Mart that includes all the data points and historical data for the BSA/AML/OFAC area. This will bring efficiencies by enabling the 100% automation of metrics, will reduce risks by improving data quality and consistency. In adition, this project has an strategic approach. |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No: No; Low: Very Low; Low: Moderate; Low: Low; Low: Low; Low: Low | 12+ Months | Execution | Low | Finance Impact Very low, Customer Impact Low, Regulatory impact is considered Moderate, Reuptional impact remains low. | BCO approved risk assessment on 04/24/2025. | Strategy;Technology; (IT Change) | 1/1/2025 | 7/31/2025 |  | 7/30/2026 | Green | NA | NA | No | Transformation | 1 | Approved | 04/24/2025 | 2025-01-02 | 2026-12-03 | 2026-08-30 | 2025-01-16 | 2025-01-27 | A | A | Decrease | Low | Low | Low | N/A | $ 0 | Active | Waterfall | No | Green |  |  | Green |  |  | Green |  |  | Green |  |  | Green |  |  | Continue with Data Mapping and Identifications |  |  |  | Yes |  |  | No |  |  |  | 3506 | 31110
72037 | 3338 | Debit Card | BSI_Commercial |  |  |  |  | Approved | 01/29/2025 02:42:04 PM | Joshua De Leon | Eugenio Alvarez | Maria Fernanda Lopez | NA |  |  | BSI | Add to BSI’s product portfolio debit and credit cards with new features, a new value proposition, and improve customer experience (fraud control tools, online services): Debit Cards: relaunch debit card Credit Card: launch a new credit card | CommercialREVF;Technology;Operations; |  | Yes | Yes | IT Projects | L: > $2M | Yes | No | Yes | High | Very Low | N/A | N/A | N/A | N/A | Moderate | N/A | Moderate | Very Low | Yes | 12+ Months |  | High | n |  | NPBA;Technology; | 08/05/2023 | 12/31/2025 |  | 02/14/2025 | On Hold | NA | NA | Yes | Profitable Growth; | 1 | Missing |  |  |  |  | 2025-01-27 17:49 | 2025-01-29 14:42 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  |  | No |  |  | No
72028 | 3264 | Derivatives Non-Deliverable Forwards NDF | BSI_Treasury and Markets | T24 | Yes | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Ted Fernandez | Jose Maria Lafora | Megia Planet, Domingo |  |  | BSI | Expanding the product catalogue by offering the NDF product to the clients allowing them to have better ability to mitigate their investment portfolios risks by hedging and to optimize the returns in their investments. | Technology;Operations | Jose Oliveros |  | Yes | IT Projects | M: $500k - $2M | No: No; Low: Moderate; Low: Moderate; Low: Moderate; Low: Moderate; Low: Low | 12+ Months | Closed | Moderate | Financial Impact- Moderate Customer IMpact- Moderate Regulatory Impact- Moderate Reputational Impact- Low |  | Strategy;Technology; (IT Change) | 6/30/2024 | 12/12/2025 | 9/2/2026 5:36:36 PM | 05/27/2026 | Complete | NA | NA | No | Profitable Growth | 1 | Approved | 10/23/2025 |  |  |  | 2025-01-24 | 2025-01-24 | B3P | B3P | Stable | Moderate | Low | N/A | N/A | $ 0 | Non Active |  | No | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | Working to close project as all the milestones have been sucessfully completed. |  |  |  | Yes |  |  | No |  |  | Savings and Investments
72140 | 3275 | Derivatives OTC Customer-ALCO - IRDs- IRS, CCS, Caps-floors & Swaptions | BSI_Treasury and Markets |  |  | None |  | Approved | 01/27/2025 04:27:44 PM | Joshua De Leon | Ricardo Marin Bataller | Jose Maria Lafora | NA | None | None | BSI | Expanding the product catalogue by offering the IRDs to clients allowing them to have better ability to mitigate their investment portfolios risks by hedging and to optimize the returns in their investments. This is aligned with BPI strategy of improving Bank competitiviness, atending client´s demand of products and increase revenues, volume of clients and AUM. At the same time, expanding business capabilities in ALCO desk allowing a wide range of hedging strategies. | Technology;Operations; |  | Yes | Yes | IT Projects | L: > $2M | Yes | No | Yes | Moderate | Moderate | N/A | N/A | N/A | N/A | Moderate | N/A | Moderate | Very Low | No | 6-12 Months |  | Moderate | n |  | Technology;BusinessActivity; | 04/01/2025 | 12/31/2025 |  | 07/23/2025 | On Hold | NA | NA | No | Profitable Growth; | 1 | Missing |  |  |  |  | 2025-01-27 08:43 | 2025-01-27 16:28 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | Treasury area has decided to cancel this project due to the need on focusing in other that are on-going and are more required to be completed and also to satisfy two new initiatives recently on boarded. |  |  |  | No |  |  | No
72155 | 3533 | Digital Channel | BSI_Technology |  |  | IT for IT |  | Approved | 02/20/2025 11:56:37 AM | Joshua De Leon | Javier Rodriguez Hergueta | Elizabeth Noda | NA | None | None | BSI | Implement digital channels in BSI to support multiple workflows. | Technology; |  | Yes | Yes | IT Projects | L: > $2M |  | No | No | Very Low | Very Low | N/A | N/A | N/A | N/A | Very Low | N/A | Very Low | Very Low | No | 6-12 Months |  | Very Low | s |  | Technology; | 01/01/2025 | 12/31/2025 |  | 01/23/2026 | On Hold | NA | NA | No | Simplification; | 1 | Missing |  |  |  |  | 2025-02-20 11:34 | 2025-02-20 11:57 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | Project cancelled due to re-prioritization of strategic initiatives and resources restrictions |  |  |  | No |  |  | No
31423 | 31423 | Digital Notarization Service (by Docusign) | BSI_Commercial |  |  | N/A | Joshua De Leon | Approved |  | Jose Lafarga | Jose Lafarga | Carolina Alvarez | Jose Lafarga | NA | NA | BSI | This proposal aims to implement a digital notarization service by leveraging the existing team of notaries within the Commercial Area to authenticate client signatures required during the onboarding process. The service would be provided through DocuSign as an additional functionality. The platform enables secure video conferencing, allowing clients and our notaries to participate remotely in the notarization process. All interactions and documents would be recorded, validated, and notarized within the platform, ensuring full compliance and an auditable trail. |  | N/A, Non-IT project |  |  | Non-IT Projects | S: < $500k | Yes | No | Yes | Very Low | Very Low | Low | Low | Very Low | Very Low | Very Low | Low | Very Low | Very Low | No | 0-6 Months | Execution | Low | Overall Materiality Assessment is low, due to materiality assessment matrix review. |  | BusinessActivity; | 1/23/2026 | 10/5/2026 |  |  |  | NA | NA | No | Simplification | 0 | Approved | 08/17/2026 |  |  |  |  | 2026-01-26 | L | L | Stable | Low | Low | N/A | N/A | $ 0 | Active | Waterfall | No | [19 empty] | No |  |  | No |  |  | Savings and Investments |  | 31423
72138 | 3267 | Digital Wealth | BSI_Premier Banking |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Luis Sanchez Huerta | Jose Maria Lafora | Patricia Correa | None | None | BSI | A technology-enabled platform that will provide digital wealth management services to lower wealth band segments and new generations from LatAm to US |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No: No; Low: Low; Low: Low; Low: High; Low: High; Low: Moderate | 12+ Months | Execution | High | Financial Impact - Low Customer Impact- High Regulastory Impact - Low Reputational Impact- Moderate |  | NPBA;Technology; (IT Change) | 9/9/2022 | 9/30/2025 |  | 9/23/2026 | Green | NA | NA | Yes | Transformation | 1 | Approved | 07/08/2025 | 2024-02-02 | 2027-02-24 | 2026-09-18 | 2025-01-16 | 2025-01-27 | A | A | Increase | High | Moderate | Moderate | N/A | $ 0 | Active | Hybrid | Yes | Green |  |  | Green |  |  | Green |  |  | Green |  |  | Green |  |  | - R01, R02, R03-W1, R03-W2 currently in PRO. -New developments will be presented to complete Delivery hub Process. -R04 presented in Gate 04. Development in progress. -R05, R06, R07 and R08 presented in Gate 03 |  |  |  | Yes |  |  | No |  |  |  | 6223, 6112 | 31106
72778 | 3512 | Discretionary Portfolio Mandate | BSI_Products and Investments |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Alejandro Uriarte | Cynthia Morzan | Daniela De La Torre |  |  | BSI | Automation DPM. Currently, DPM creates and updates manually all the information uploaded in 360. We need automation in all the steps of the workflow. We request a consultant to work together with IT (Data Analytics) for the automation of the flow chart. All the information is within Medea. |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No: Yes; No: No; Low: Moderate; Low: Moderate; Low: Low; Low: Very Low; Low: Low | 6-12 Months | Closed | Low | n | BCO approved risk assessment on 09/15/2025. | Technology; (IT Change) | 8/30/2024 | 4/30/2025 | 3/30/2026 7:41:48 PM | 03/31/2026 | Complete | NA | NA | No | Simplification | 1 | Approved | 09/15/2025 |  |  |  | 2025-02-19 | 2025-02-20 | B3P | B3P | Stable | Low | Low |  | N/A | $ 0 | Non Active |  | No | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | The project has been completely completed. |  |  |  | No |  |  | No
72830 | NA | DM Change Management Work-Flow | BSI |  |  |  |  | Saved | 03/20/2025 12:42:28 PM | Ana Cabezuelo | Alfredo Aguila |  | NA |  |  | BSI | Create with Power Automate a simple workflow to control the changes in the BSA/AML/OFAC Data Mart. | Technology; |  | Yes | No | Non-IT Projects | S: < $500k |  | No | No | Very Low | Very Low | N/A | N/A | N/A | N/A | Very Low | N/A | Very Low | Very Low | No | 0-6 Months |  | Very Low | No materiality. This is a simple workflow that will replace email workflows reducing errors. |  | BusinessActivity; | 05/01/2025 | 05/30/2025 |  |  |  | NA | NA | No | Simplification; | 0 | Missing | [6 empty] | N/A | NA | [5 empty] | NA | Non Active |  | NA | [19 empty] | No |  |  | No
30579 | 30579 | Email Enhancement Opt - out Func | BSI_Risk |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Bonilla, Rafael | Jose Maria Lafora | Carlos de Lemos | None | None | BSI | This covers addiontal requirements associated with implementation CAN-SPAM Regulation within our email to customers process. Related to marketing activities. The regulation is already applicable and implemented within the marketing tool application and now needs to be expanded to all emails from commercial team. |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No: No; Yes: No; Low: Very Low; Low: Moderate; Low: Moderate; Low: Moderate; Low: Moderate; No: No | 6 - 12 months | Canceled | Moderate | Financial Impact - The financial impact is deemed as low because the budget for the project is 55,000. Customer Impact - Moderate customer impact as it improves the current process that exist today. Regulatory Impact - This is related to CAM-SPAM regulation. Option to customers to opt out of marketing emails. Reputational Impact - Moderate as customers may complain they have not been opted out after sending the communication. |  | Technology; (IT Change) | 1/1/2026 | 12/31/2026 |  | 02/06/2026 | On Hold | NA | NA | No | Must-Do | 1 | Missing |  |  |  |  | 2026-01-08 | 2026-01-09 | A | A | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | it was decided that the project will be cancelled - not required |  |  |  | Yes |  |  | No |  |  | Risk
31884 | 31884 | Equity Recommended List Framework Update | BSI_Products and Investments |  |  | Investments | Joshua De Leon | Approved |  | Igor Ugarte | Julio Zapata | Belen Monzon | Igor Ugarte |  |  | BSI | The BSI CIO is presenting for notification an update in the methodology used by Global Wealth Management Division (WMD) to define the Global Equities Matrix (Equity Universe) that applies to different Private Banking units across the Group. This change has been approved by the Corporate Compliance Forum on 11/26/2025. This Framework has been revised and cascaded down from the Wealth Management Division (WMD). As established in BSI approved Framework from 10/27/202, BSI receives a file from WMD on a quarterly to update the Equity Universe. There is no change to this procedure. BSI is looking to adhere to the updated Equity Matrix and new selection parameters. This change has been reviewed by BSI Chief Information Officer and by the Fiduciary Risk Unit during January 2026. | Risk | N/A, Non-IT project |  |  | Non-IT Projects | S: < $500k |  | No | No | Very Low | Very Low | Very Low | Very Low | Low | Very Low | Very Low | Very Low | Very Low | Very Low | No | 0-6 Months | Closing | Low | this initiative is assessed as Low overall, with Low Strategic/Business impact. The change updates/adheres to WMD equity recommended-list methodology and selection parameters without changing BSI's quarterly update procedure. Financial, Regulatory/Compliance, Third-Party, IT, Innovation, Reputational/Customer and People impacts are Very Low because it is a framework/methodology update reviewed through existing governance and controls. |  | BusinessActivity; | 1/23/2026 | 1/30/2026 |  |  |  | NA | NA | No | Global Connectivity | 0 | Approved | 07/23/2026 |  |  |  | 2026-01-23 | 2026-01-26 | L | L | Stable | Low | Low |  | N/A | $ 0 | Active | Waterfall | No | [19 empty] | No |  |  | No |  |  | Savings and Investments |  | 31884
72949 | 3732 | Family Office - Phase 1 | BSI_Strategy |  |  |  |  | Approved | 06/25/2025 03:08:47 PM | Cristian Krossler | Ximena Ardila | Jose Maria Lafora | NA |  |  | BSI | Launch Phase 1 Family Office platform aimed at delivering holistic, wealth advisory and consulting services to Ultra-High-Net-Worth (UHNW) clients. Phase 1 main objective is to hire a specialized team that could grow BSI’s client portfolio, while integrating in-house family office expertise. This phase will focus on onboarding the newly recruited team’s client portfolio consisting on 11 family groups, and building the capabilities required to advise on the client’s entire wealth, including externally held assets. | HR;Finance;Operations;Risk;Legal; |  |  | No | Non-IT Projects | S: < $500k |  | No | No | Moderate | Moderate | N/A | N/A | N/A | N/A | Moderate | N/A | Moderate | Moderate | No | 0-6 Months |  | High | The new service will be only offered to 11 Family groups in Phase 1. Risk management process through family office platform seeks to identify and assess investment decisions following a comprehensive approach based on goals, values and risk tolerance of clients, leveraging from the expertise BSI has implemented in the wealth management segment with robust controls on sales practices and disclosures | BCO approved risk assessment on 07/08/2025. | NPBA; | 06/30/2025 | 12/31/2025 | 3/10/2026 5:11:50 AM | 01/06/2026 | Complete | NA | NA | Yes | Profitable Growth; | 1 | Approved | 01/16/2026 |  |  |  | 2025-06-25 08:39 | 2025-06-25 15:09 | H | NA | Stable | High | Low | Moderate | N/A | NA | Non Active |  | No | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | N/A |  |  | Initiative designed to position the bank competitively in a shifting wealth management landscape that increasingly favors hybrid service models. Moving project to closing |  |  |  | No |  |  | No
73021 | 3768 | Family Office Platform | BSI_Strategy |  |  | N/A | Joshua De Leon | Approved |  | Cristian Krossler | Ximena Ardila | Jose Maria Lafora | Cristian Krossler |  |  | BSI | Build capabilities needed to advise on the client’s entire wealth, including externally held assets. Initiative designed to position BSI competitively in a shifting wealth management landscape, and alligned to the strategic priorities around UHNW clients |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No: No; No: No; Low: Moderate; Low: Low; Low: Moderate; Low: Moderate; Low: Low | 6-12 Months | Execution | High | Service directed to UHNW clients, estimating to serve ~20 clients during the first 3 years | BCO approved risk assessment on 10/30/2025. | NPBA;Technology; (IT Change) | 8/29/2025 | 8/31/2026 |  | 10/1/2026 | Green | NA | NA | Yes | Profitable Growth | 1 | Approved | 09/29/2026 | 2025-01-02 | 2026-10-30 | 2026-09-14 | 2025-08-22 | 2025-08-25 | B3P | B3P | Stable | High | Low | Moderate | N/A | $ 0 | Active | Waterfall | Yes | Green |  |  | Green |  |  | Green |  |  | Green |  |  | Green |  |  | The Family Office - Presented to Gate 5 |  |  |  | No |  |  | No |  |  |  | 7949 | 31243
72856 | 3666 | Fed Import-FED Export (FIS) | BSI_Operations |  |  | N/A | Joshua De Leon | Approved |  | Claudia Romero | Maria Teresa Del Cerro | John Pendas | Rolando Bonilla | 005056BCB79A1EBE83EA49172F58EE | ISAR DD's(FedLink/Fed Export/Import, ACH Express,Testkey and Mastercard Connect) | BSI | Fed import: Is our current tool for processing incoming checks for our clients, it is linked to the Federal Reserve Bank (FED). The tool also generates report requested for Audits, storages images of checks and process check returns. It is connected to our core T24 to debit our clients and send any controls the account may have. Through this process we verify all the information of the check. FedExport: Is our current tool for checks we deposit at the teller. After the checks are deposited it generates a file containing the information processed on the checks and are sent to the Federal Reserve Bank (FED). FedExport generates reports for audits, storages images for checks, Interbanks, Check on Us deposited, Cash Out, and Returned checks among other reports we use internally for compliance and our department. | Technology;Operations | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No: No; Low: Low; Low: Low; Low: Moderate; Low: Moderate; Low: Very Low | 6-12 Months | Planning | Moderate | Materiality based on this service affecting between 2-5% of our clients (-450). |  | Strategy;NPBA;Technology; (IT Change) | 4/30/2025 | 6/30/2026 |  | 10/27/2025 | On Hold | NA | NA | Yes | Must-Do | 1 | Missing |  | 2025-01-02 | 2025-12-31 | 2026-08-29 | 2025-04-10 | 2025-04-10 | B3P | B3P | [5 empty] | $ 0 | Non Active | Waterfall | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | Legal reviewing contract with Vendor FORUM has approved project PIF approved Delivery HUB in process Gate 3 activated Follow up with domains meeting to review contract with legal look for architech solution |  |  |  | Yes |  |  | No |  |  |  |  | 31114
72775 | 3602 | Finance Monthly Checklist Digital Form (Appian) | BSI_Finance | Appian | No | N/A | Joshua De Leon | Approved |  | Joshua De Leon |  | Jose Maria Lafora | Sadis Alvarenga |  |  | BSI | The project aims to enhance efficiency and accuracy in the Month-End Checklist process by transitioning from a manual, PDF-based system to a centralized, digital solution using Appian. Currently, the process involves manually updating an Excel spreadsheet, converting it to a PDF, and distributing it among Controllership team members for task signoffs. By leveraging Appian, the checklist will be centralized, allowing team members to sign off on their tasks digitally. Notifications and reminders will be automated, ensuring timely completion of their processes. |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No: Yes; No: No; Low: Very Low; Low: Very Low; Low: Very Low; Low: Very Low; Low: Very Low | 0-6 Months | Closed | Low | n | BCO approved risk assessment on 04/22/2025. | Technology; (IT Change) | 1/1/2025 | 4/1/2025 | 2/18/2026 2:42:10 PM | 01/22/2026 | Complete | NA | NA | No | Transformation | 1 | Approved | 07/18/2025 |  |  |  | 2025-02-19 | 2025-02-21 | B3P | B3P | Stable | Low | Low | Very Low | N/A | $ 0 | Non Active |  | No | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | Moving project to Closing |  |  |  | No |  |  | No
72163 | 3270 | Financial Data Mart (Tablaeu) | BSI_Finance | Tablaeu | No | None |  | Approved | 01/27/2025 04:00:01 PM | Joshua De Leon | Eloina Franco-Espinosa | Jose Maria Lafora | NA | None | None | BSI | Develop a Data Mart for the specific needs of the Finance Department and/or a Domain Area (TBD) Phase I: Complement Medea with missing Finance data and implement Sox Compliance Controls / Processes in subset of Medea (the Finance Data Mart) Phase II: Incorporate advance analytics tools in a focused Finance Data Mart to the enhance decision making process | Finance;Technology; |  | Yes | Yes | IT Projects | M: $500k - $2M | No | No | Yes | Low | Moderate | N/A | N/A | N/A | N/A | Moderate | N/A | Low | Moderate | No | 6-12 Months |  | Moderate | Financial Impact is low, Customer Impact is Low, Regulatory impact Moderate, Reputational Impact - Moderate |  | Technology;Strategy; | 01/01/2025 | 12/31/2025 | 12/30/2025 5:10:32 PM | 12/30/2025 | Complete | NA | NA | No | Simplification;Transformation; | 1 | Approved | 08/07/2025 |  |  |  | 2025-01-16 11:07 | 2025-01-27 16:00 | ABC | NA | Stable | Moderate | Low | Low | N/A | $ 0 | Non Active |  | No | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | Moving project to Closing |  |  |  | No |  |  | No
32247 | 32247 | Fund Wrap investment service closing | BSI_Products and Investments |  |  | Investments | Joshua De Leon | Approved |  | Igor Ugarte | Julio Zapata | Jacqueline Rebhuhn | Igor Ugarte |  |  | BSI | Fund Wrap investment service will be discontinued, as it is no longer considered a strategic product. As a result, any assets currently held or invested through the Fund Wrap platform will be transferred to the Bank’s Banking & Investment Services (“BIS”) platform. Currently, we have 165 clients on the platform, representing a total of USD 173 million in AUM. The plan is to close these accounts and convert them into non-discretionary accounts. | Legal;CommercialREVF | N/A, Non-IT project |  |  | Non-IT Projects | S: < $500k |  | No | No | Very Low | Very Low | Very Low | Very Low | Low | Very Low | Low | Very Low | N/A | N/A | No | 0-6 Months | Execution | Low | no change |  | BusinessActivity; | 6/1/2026 | 9/30/2026 |  | 6/17/2026 | Not Started | NA | NA | No | Simplification | 0 | Approved | 06/26/2026 |  |  |  | 2026-06-09 | 2026-06-10 | L | L | Stable | Low | Very Low |  | N/A | $ 0 | Active | Waterfall | No | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | The Fund Wrap investment service closing Project has been created. |  |  |  | No |  |  | No |  |  | Savings and Investments |  | 32247
31895 | 31895 | GPT Analisis de transacciones y de Negative Media | BSI_Risk |  |  | N/A | Joshua De Leon | Approved |  | Ana Cabezuelo | Maria Martinez | Jose Maria Lafora | Ana Cabezuelo |  |  | BSI | The GPT will help analyst in their activities related to transactions analisis and negative media searches by preparing docs drafts that will be finalized and completed by the analyst. | Risk | N/A, Non-IT project |  |  | Non-IT Projects | S: < $500k |  | No | No | Very Low | Low | Low | Low | Low | Low | Very Low | Low | Very Low | Very Low | No | 0-6 Months | Execution | Low | Financial: Very low because we don't see risk asociated to financial impacts as there is no direct budget to be consumed. Customer: This does not interfere with the Customer Regulatory: We are non changing the process in a way that could bring regulatory impact Reputational: We don't feel any potential reputational impact due to this change. |  | BusinessActivity; | 3/4/2026 | 3/27/2026 |  |  |  | NA | NA | No | Simplification | 0 | Missing |  |  |  |  | 2026-04-02 | 2026-04-20 | L | L | [5 empty] | $ 0 | Active | Waterfall | No | [19 empty] | No |  |  | No |  |  | Savings and Investments |  | 31895
73089 | NA | ICAV Inclusion Framework | BSI_Products and Investments |  |  | Products |  | Out Of Scope - Approved | 11/14/2025 10:03:04 AM | Igor Ugarte | Ivan Howard | Cynthia Morzan | NA |  |  | BSI | Onboard the framework to set out the principles and criteria governing the inclusion of third-party alternative investment funds. Its purpose is to ensure a disciplined, transparent, and regulatorily compliant approach to fund selection, on boarding, and ongoing oversight, aligned with our fiduciary duties and risk appetite. Applies to all new alternative investment funds offered as feeder funds of PRIVA or Laurion, Irish Collective Asset Vehicles (ICAVs). The objective is to safeguard investor interests through consistent due diligence, monitoring, and on-boarding standards. | Risk;Legal; |  |  | No | Non-IT Projects | S: < $500k |  | No | No | Very Low | Low | N/A | N/A | N/A | N/A | Very Low | N/A | Very Low | Very Low | No | 0-6 Months |  | Low | . |  | BusinessActivity; | 11/12/2025 | 12/31/2025 |  |  |  | NA | NA | No | Simplification; | 0 | Missing |  |  |  |  | 2025-11-14 10:01 | 2025-11-14 10:03 | N/A | NA | [5 empty] | NA | Non Active |  | NA | [19 empty] | No |  |  | No
72776 | 3520 | Informatica Data Management Cloud | BSI_Technology |  |  |  |  | Approved | 02/20/2025 11:29:53 AM | Joshua De Leon | Jose Oliveros | Elizabeth Noda | NA |  |  | BSI | This initiative aims to replace our obsolete ETL software with Informatica Data Management Cloud (IDMC) to improve data integration, scalability, and efficiency. The current system is outdated, costly to maintain, and limits our ability to manage growing data needs. IDMC offers a solution with better security, and enhanced data handling capabilities. This transition will reduce risks, future-proof our data infraestructure, and support long-term business growth. (ETL) | Technology; |  | No | Yes | IT Projects | S: < $500k |  | No | No | Very Low | Very Low | N/A | N/A | N/A | N/A | Very Low | N/A | Very Low | Very Low | No | 6-12 Months |  | Very Low | n |  | Technology; | 11/01/2024 | 03/31/2025 |  | 12/15/2025 | On Hold | NA | NA | No | Simplification;Transformation; | 1 | Approved | 11/12/2024 |  |  |  | 2025-02-19 15:11 | 2025-02-20 11:30 | ABC | NA | Stable | Critical | Critical | Low | N/A | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | We decided to cancel this project because there is no need for this tools as we have decided to use POSIT as official ETL tool for the bank. |  |  |  | No |  |  | No
72151 | 3260 | ISO20022 | BSI_Operations |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Maria Teresa Del Cerro | John Pendas | Daniel Abdelnour |  |  | BSI | Implement FEDLINK for SWIFT ISO 20022 translation, validation, and processing by routing inbound and outbound SWIFT messages through MQ, OFAC Verifier / One FCC, and a new consolidated Payment Monitor. The change will replace legacy SWIFT workflows, the SWIFT Interface Monitor, and the existing FEDWIRE Payment Monitor, while also incorporating ACH OFAC routing and structured/hybrid address support for SWIFT/FED compliance. | Operations;Technology;Finance;Risk | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No: No; Yes: No; Low: Low; Low: Moderate; Low: High; Low: High; Low: Low | 12+ Months | Planning | High | Financial Impact will remain low, Custome impact is high. Regulatory is deemed Moderate with Reuptional Impact remaining low. |  | Regulatory;Technology; (IT Change) | 6/30/2024 | 3/28/2025 |  | 7/31/2026 | Green | NA | NA | No | Must-Do | 1 | Missing |  | 2025-02-14 | 2027-06-29 | 2026-08-29 | 2025-01-16 | 2025-01-23 | B3P | B3P | [5 empty] | $ 0 | Active | Waterfall | Yes | Green |  |  | Green |  |  | Green |  |  | Green |  |  | Green |  |  | ISO 20022 work has shifted from the original single-track approach to a dual-release plan covering the November release and related Fedlink changes. The team is aligned on the required T24, Swift, MQ, Fedlink, and Ocean System adjustments, with testing and validation now being coordinated across business and technical stakeholders. Current focus is on finalizing scope/documentation separation, completing parallel testing, and preparing the release for controlled deployment |  |  |  | Yes |  |  | No |  |  |  |  | 31101
32096 | 32096 | Karta | BSI_Commercial |  |  | N/A | Joshua De Leon | Approved |  | Bruno Da Silva | Jose Lafarga | Carolina Alvarez | Bruno Da Silva |  |  | BSI | The initiative aims to introduce a charge card solution for the Digital Wealth segment through a partnership with a third-party fintech provider (Karta). This will complement the existing Cornercard offering by providing a faster onboarding process, simplified value proposition, and scalable servicing model tailored to clients with lower AUM. The solution leverages a multi-issuer model and digital servicing capabilities (including app and messaging-based support), enabling the Bank to enhance client engagement, expand product penetration, and improve competitiveness in the digital segment. | CommercialREVF | N/A, Non-IT project |  |  | Non-IT Projects | S: < $500k | No | No | Yes | Low | Moderate | Moderate | Low | Low | Very Low | Moderate | Very Low | N/A | N/A | No | 6 - 12 months | Planning | Moderate | The overall criticality remains manageable as no technology development or integration with BSI systems is required, and the initiative operates within existing governance and vendor oversight frameworks. The change is limited to enhancing digital servicing capabilities for the Digital Wealth segment without impacting core banking operations. |  | NPBA; | 5/20/2026 | 12/30/2026 |  | 9/22/2026 | Green | NA | NA | Yes | Profitable Growth | 1 | Missing | 09/28/2026 | 2026-01-02 | 2026-12-31 | 2026-08-29 | 2026-05-27 | 2026-05-28 | H | H |  |  |  |  | N/A | NA | Active | Waterfall | No | Green |  |  | Green |  |  | Green |  |  | Green |  |  | Green |  |  | The status of the project is green, no issue reported. |  |  |  | No |  |  | No |  |  | Cards |  | 32096
72148 | 3273 | Lynx - Fraud Tool | BSI_Operations |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Maria Teresa Del Cerro | Jose Maria Lafora | Carlos de Lemos |  |  | BSI | Lynx – Fraud detection and prevention tool. The benefit of this project is to automate the current manual process which may be subject to regulatory findings. This tool is already implemented in other entities and belongs to the group. This is a new capabilities needed to support the new digital strategy. | Operations | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No: Yes; No: No; Yes: Yes; Low: Moderate; Low: Low; Low: Moderate; Low: N/A; Low: N/A | 12+ Months | Execution | Moderate | Financial Impact- Moderate Customer IMpact- Moderate Regulatory Impact - Low Reputational Impact - Very Low |  | Technology; (IT Change) | 1/2/2024 | 12/31/2026 |  | 8/31/2026 | On Hold | NA | NA | No | Transformation | 1 | Approved | 07/17/2025 | 2025-01-02 | 2026-11-02 | 2026-08-31 | 2025-01-16 | 2025-01-27 | B3P | B3P | Stable | Moderate | Low | Low | N/A | $ 0 | Non Active | Waterfall | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | Project on hold as we are defining required specifications for next release. |  |  |  | No |  |  | No |  |  |  | 7415 | 31233
31826 | 31826 | Maisa AI Agents - BSI | BSI_Strategy |  |  | N/A | Joshua De Leon | Approved |  | Rodrigo Puga | Ximena Ardila | Jose Maria Lafora | Rodrigo Puga |  |  | BSI | Implement AI-powered digital workers with Maisa to automate selected high-impact and control-intensive processes, following a use case driven approach, with the objective of improving consistency, strengthening decision-making, reducing operational risk, and enhancing efficiency across all business areas within BSI | Technology;Risk | Jose Oliveros |  | Yes | IT Projects | S: < $500k | Yes | No | Yes | Very Low | Low | Low | Moderate | Moderate | High | Low | Very Low | N/A | N/A | No | 6 - 12 months | Planning | High | Customer Information Organizer Financial - Very Low We don’t expect to spend more than 100k on the project or see any financial impact caused by it. This assumes we are isolating the KYC use case Regulatory & Compliance Risk - Low Direct implications of this project are very low. All KYC information required by regulators will remain in our systems, and the new way of organizing it will be validated by the customer owners Third Party Dependency - Low Given that KYC is a one-off project, we don’t have ongoing risk. In the short-term interaction with the vendor, we do not foresee risk, as the vendor is supported by the group through strategic initiatives and venture funding Information Technology - Moderate Integration between two systems is required, making it a multi-system setup. API development is something the technical team are familiar with and have done for other system integrations. We are also very familiar with the required developments in the data mart and what this entails Strategic / Business Impact - Moderate The project is important for the transformation strategy of the AML department and helps accelerate it, but it is not a critical process or project Innovation / Emerging Risk - High This involves the new MAISA platform, which has not been used at BSI before Reputational / Customer Risk - Low The customer has no external visibility that this process has taken place. The only potential interaction is from the commercial team requesting any missing information that was not captured during the initial KYC People / Change Adoption - Very Low The KYC and KYC refresh processes will remain the same; the only change is how the information is presented Correspondent Bank Financial - Very Low We expect financial impact to be lower than 100K Regulatory & Compliance Risk - Low This use case touches wire transfers, payment processing, and customer/payment data in a regulated banking environment. Even though the solution is internal and supports existing controls, anything that influences payment routing or completion has regulatory visibility Third Party Dependency - Low Although the use case relies in part on LexisNexis as an external data source, the dependency appears manageable rather than critical. The third party supports the identification process, but the bank still retains internal workflow control, historical data, and operational oversight Information Technology - Moderate The use case requires systems integration. The technical scope is contained within an existing operational environment, working within existing systems such as T24. The implementation is targeted and operationally specific, with limited technical exposure outside the use case itself Strategic / Business Impact - Moderate This use case supports an important operations efficiency objective by improving the speed, consistency, and scalability of wire transfer processing. It addresses a real operational bottleneck and could produce noticeable benefits in productivity, turnaround time, and service quality Innovation / Emerging Risk - High The solution involves a new agentic AI platform that has been approved by group and US Reputational / Customer Risk - Low If the solution selects the wrong correspondent bank or causes payment delays/rejections, customers could be impacted and fees or dissatisfaction could result. But since there is still a human quality check before final authorization, this reduces the risk People / Change Adoption - Very Low This use case appears to enhance an existing operations workflow rather than fundamentally changing roles, organization structure, or the process. Users would continue working within familiar processes, with the solution acting as a support mechanism rather than requiring broad reskilling or major behavioral change |  | BusinessActivity;Technology; (IT Change) | 4/10/2026 | 12/31/2026 |  | 8/26/2026 | Red | NA | NA | No | Simplification | 1 | Approved | 07/23/2026 | 2025-09-26 | 2026-12-31 | 2026-08-29 | 2026-04-08 | 2026-04-08 | B3P | B3P | Stable | Moderate | Low | High | N/A | $ 0 | Active | Waterfall | Yes | Green |  |  | Green |  |  | Red | Schedule is being reported in Amber due to the fact that the vendor has been delayed +30 days. The team was dependent on the vendor going live with the Maisa platform in order to be able to deploy the | 10/30/2026 | Green |  |  | Amber | Group/Maisa are currently working on remediating the vulnerabilities that were found within the platform. Local IT is not responsible for the delays but more Group IT/Maisa. | 10/30/2026 | Maisa AI Agents - BSI |  |  |  | No |  |  | No |  |  | Savings and Investments | 7810, 8126, 8127, 8128, 8130, 3299, 7051, 3344, 8129, 8149 | 31826
31147 | 31147 | Management Solutions - One Reporting | BSI_Finance |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Lina Acuna | Jose Maria Lafora | Julio Leanez | None | None | BSI | Corporate Requirement - Financial Information |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k | Yes | No | Yes | Moderate | High | Low | Low | Low | Low | Moderate | Low | Very Low | Moderate | Yes | 12+ Months | Board Approved | High | this initiative is assessed as High overall with High Regulatory/Compliance risk. The project supports corporate financial information/reporting, so a failure could affect formal regulatory or management reporting and create regulatory attention. Financial and Reputational/Customer impacts are Moderate because reporting quality can influence management decisions and stakeholder confidence. Third-Party, IT, Strategic/Business, Innovation and People impacts are Low because delivery and adoption are expected to be manageable within existing processes. |  | Technology; (IT Change) | 1/1/2026 | 12/31/2028 |  | 01/28/2026 | Not Started | NA | NA | No | Simplification | 0 | Missing |  |  |  |  | 2026-01-08 | 2026-01-14 | B3P | B3P | [5 empty] | $ 0 | Non Active |  | Yes | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  |  | Yes |  |  | No |  |  | MIS (all financial and non-financial information)
72910 | 3736 | Market Rates | BSI_Treasury and Markets |  |  | N/A | Joshua De Leon | Approved |  |  | Ted Fernandez | Jose Maria Lafora | Megia Planet, Domingo |  |  | BSI | This project aims to automate and streamline market rate management for Treasury BSI Miami by integrating Polar Lake and MEDEA. It will remove manual intervention so Operational risk will be decreased. Also it will reduce work overload in the Area. Additionally to the automation, a complementary Appian workflow will be created to ensure Treasury users monitor correct automatic uploading and facilitating the user the option of making adjustments where needed. | Finance;Technology;Operations | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No: No; Low: Very Low; Low: Very Low; Low: Very Low; Low: Very Low; Low: Very Low | 6-12 Months | Canceled | Very Low | No financial impact since this will not increase income neither cost. Transparenct for the client. Related to ALCO activities. This will no create any regulatory breach but automation will reduce operational risk by remoding manual intervention. No reputuational risk from doing this activity under new process. |  | Strategy;Technology; (IT Change) | 5/22/2025 | 12/18/2025 |  | 05/14/2026 | On Hold | NA | NA | No | Simplification | 1 | Missing |  |  |  |  | 2025-05-22 | 2025-05-22 | A | A | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | ePMO Forum with CEO and CIO intervention decided cancelation of this project as benefit from its excution were not a priority for BSI |  |  |  | Yes |  |  | No
73119 | 3823 | MATCHBOX | BSI_Risk |  |  |  |  | Approved | 12/09/2025 05:48:19 PM | Carlos de Lemos | Maria Martinez | Jose Maria Lafora | NA | N/A | N/A | BSI | This is a request to enable firewall access to Group's portal MATCHBOX. This portal is used to allow compliance with a requirement from wealth management Division to provide data about our customers, whcih is used by WMD to reiew common customer base across the different PB units. | Technology;Risk; |  |  | No | IT Projects | S: < $500k | No | No | Yes | Very Low | Very Low | N/A | N/A | N/A | N/A | Low | N/A | Low | Very Low | No | 0-6 Months |  | Low | Not applicable |  | Technology; | 01/02/2026 | 01/30/2026 |  |  |  | NA | NA | No | Must-Do; | 0 | Missing |  |  |  |  | 2025-12-05 10:31 | 2025-12-09 17:48 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | [19 empty] | No |  |  | No
72136 | 3217 | Mature Info sec projects | BSI_Technology |  |  | IT for IT | Joshua De Leon | Approved |  | Joshua De Leon | Dayam Borges | Elizabeth Noda | Evelio Heredia |  |  | BSI | Project that combine differente efforts and solutions to mature our current Infosec Processes to maintain and strenghten BSI enviroment. Also provide alignment with the Go to Model from Santander Group. This project includes different efforts but not limited to * Firewalls * Hardening * Maturity | Technology | Jose Oliveros |  | Yes | IT Projects | L: > $2M | No: No; Low: Low; Low: Very Low; Low: Very Low; Low: Very Low; Low: Very Low | 12+ Months | Concept Development | Low | d |  | Technology; (IT Change) | 1/4/2024 | 12/31/2025 |  | 06/01/2026 | Green | NA | NA | No | Simplification | 1 | Missing |  | 2025-01-02 | 2026-12-31 | 2026-08-29 | 2025-01-17 | 2025-01-17 | CND | CND | [5 empty] | $ 0 | Active | Waterfall | No | Green |  |  | Green |  |  | Green |  |  | Green |  |  | Green |  |  | R1: On Track. Team is working on developing the scope for the additonal releases. |  |  |  | Yes |  |  | No |  |  |  |  | 31097
72156 | 3261 | Mature Infrastructure | BSI_Technology |  |  | IT for IT | Joshua De Leon | Approved |  | Joshua De Leon | Jose Oliveros | Elizabeth Noda | Raul Fort |  |  | BSI | these solutions will mature our current Infrastructure to maintain strenghten our enviroment. | Technology | Jose Oliveros |  | Yes | IT Projects | L: > $2M | No: No; Low: Moderate; Low: Very Low; Low: Very Low; Low: Very Low; Low: Very Low | 6-12 Months | Planning | Moderate | Financial Impact - Moderate Customer Impact- Very Low Regulatory Impact- Very Low Reputational Impact- Very Low |  | Technology; (IT Change) | 1/1/2025 | 12/31/2028 |  | 9/23/2026 | Green | NA | NA | No | Must-Do | 1 | Approved | 05/05/2026 | 2025-01-02 | 2028-12-29 | 2026-08-29 | 2025-01-17 | 2025-01-17 | CND | CND | Stable | Moderate | Low |  | N/A | $ 0 | Active | Waterfall | No | Green |  |  | Green |  |  | Green |  |  | Green |  |  | Green |  |  | Project is reporting in green, with no material risk/issues. This project will have a total of 9 releases enhancing infrastructure and governance within BSI Technology. |  |  |  | Yes |  |  | Yes |  |  | Cloud infrastructure and common IT Run | 5541 | 31102
72029 | 3620 | Mobile App revamp | BSI_Commercial |  |  |  |  | Approved | 03/17/2025 11:14:40 AM | Joshua De Leon | Eugenio Alvarez | Maria Fernanda Lopez | NA |  |  | BSI | Current Ebanking Application is outdated and has opportunities to enhance usability by rebuilding and/or substitute for new and more robust, scalable and friendly Application. | CommercialREVF;Technology; |  | Yes | Yes | IT Projects | M: $500k - $2M | Yes | No | Yes | Very Low | Low | N/A | N/A | N/A | N/A | Low | N/A | Low | Very Low | No | 6-12 Months |  | Low | n |  | Technology; | 03/25/2025 | 12/31/2025 |  | 06/10/2025 | On Hold | NA | NA | No | Simplification; | 1 | Missing |  |  |  |  | 2025-03-11 10:35 | 2025-03-17 11:15 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | This project merge into web app Web & App Backend Upgrade - 3619 (Delivery hub ID) |  |  |  | No |  |  | No
72025 | 3593 | Monitoring Improvements (ALMA, Dynatrace) | BSI_Technology |  |  |  |  | Approved | 03/06/2025 03:25:34 PM | Joshua De Leon | Jose Oliveros | Elizabeth Noda | NA |  |  | BSI | Implement monitoring tool to control and monitor our architecture. This solution will highten our current controls and avoid any future cyber threats or incidents. This will also complement our current solar winds monitoring system. | Technology; |  | Yes | Yes | IT Projects | S: < $500k | Yes | No | Yes | Very Low | Very Low | N/A | N/A | N/A | N/A | Very Low | N/A | Very Low | Very Low | No | 6-12 Months |  | Very Low | n |  | Technology; | 01/31/2024 | 12/31/2025 |  | 03/11/2025 | On Hold | NA | NA | No | Simplification;Transformation; | 1 | Missing |  |  |  |  | 2025-02-20 11:43 | 2025-03-06 15:26 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | This project has been merged into the Mature Infrastructure project |  |  |  | No |  |  | No
72779 | 3601 | NEW ASSET ALLOCATION STRUCTURE | BSI_Products and Investments |  |  | Investments |  | Approved | 02/20/2025 10:12:48 AM | Nathalie Brandon | Nicolas Perez de la Blanca Burgos | Jacqueline Rebhuhn | NA |  |  | BSI | 1. The objective of this initiative is to adjust the structure of the Asset Allocation to the new industry standards, more specifically to include a proper allocation to Alternative Investments and Digital Assets 2. We also intend to replace the current USA profile and EME profile with a Standard Private Banking Profile and a UHNWI (ultra-high net worth) profile. | Technology; |  | No | Yes | IT Projects | S: < $500k |  | No | No | Very Low | Very Low | N/A | N/A | N/A | N/A | Very Low | N/A | Very Low | Very Low | No | 6-12 Months |  | Very Low | We are adjusting the Asset Allocation structure ("buckets") in our systems to reflect today's industry's standards |  | Technology; | 02/19/2025 | 12/31/2025 |  |  |  | NA | NA | No | Transformation; | 0 | Missing |  |  |  |  | 2025-02-19 15:30 | 2025-02-20 10:13 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | [19 empty] | No |  |  | No
72773 | 3600 | NOMINEE SUBSCRIPTION | BSI_Products and Investments |  |  | Products |  | Approved | 02/19/2025 03:52:05 PM | Nathalie Brandon | Manuel Perez Duro | Jacqueline Rebhuhn | NA |  |  | BSI | The objective of this initiative is to have a Nominee set up for the subscription to private equity products, meaning have BSI act as Nominee and subscribe via an omnibus account. This is the industry standard process. Today our clients can only subscribe as direct investors and each individual documentation has to be sent to our administrator. this is one of the barrier to Alternative Investments growth. | Technology; |  | No | Yes | IT Projects | S: < $500k |  | No | No | Very Low | Very Low | N/A | N/A | N/A | N/A | Low | N/A | Low | Very Low | No | 0-6 Months |  | Low | we are aiming to align with the industry standard, allowing to subscribe with an omnibus set-up instead of our clients being direct investors to the fund |  | Technology; | 11/13/2024 | 03/31/2025 | 7/3/2025 1:26:55 PM | 06/26/2025 | Complete | NA | NA | No | Simplification;Profitable Growth; | 1 | Missing |  |  |  |  | 2025-02-19 14:38 | 2025-02-19 15:52 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | solution in production. Requested Gate 6 disposition |  |  |  | No |  |  | No
72961 | 3737 | OHIO | BSI_Products and Investments |  | No | Products | Joshua De Leon | Approved |  |  |  | Cynthia Morzan | Nathalie Brandon |  |  | BSI | We are planning to change the current provider in terms of pricing discovery for Structured Products |  | Jose Oliveros |  | No | IT Projects | S: < $500k | No: No; No: No; Low: Very Low; Low: Very Low; Low: Very Low; Low: Very Low; Low: Very Low | 0-6 Months | Closed | Low | 3rd party web application, user access to be provided to internal authorized users, following governance of 3rd party onboarding governance | BCO approved risk assessment on 09/05/2025. | Technology; (IT Change) | 7/8/2025 | 12/31/2025 | 9/2/2026 5:36:41 PM | 03/06/2026 | Complete | NA | NA | No | Profitable Growth | 1 | Approved | 09/05/2025 |  |  |  | 2025-07-08 | 2025-07-08 | B3P | B3P | Stable | Low | Low |  | N/A | $ 0 | Non Active |  | No | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | Obtained InfoSec approval and Gate 5 disposition final on 2/27 |  |  |  | No |  |  | No
72040 | 3274 | One FCC BSI | BSI_Risk |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Maria Martinez | Jose Maria Lafora | Ana Cabezuelo |  |  | BSI | The Oracle OneFCC project aims at replacing the current OFAC/Ocean screening tools by: •OneFCC Oracle’s OFSAA solution, aligning with Group’s initiatives for all the screening and enhance existing solution to comply with U.S Reguatory requirement FinCEN 314 •This implementation will homogenize the way that all Santander entities perform their screening process. The tool will increase efficiency and accuracy through a centralized technology platform in a secure, transparent, and scalable way to perform the screening process to comply with the FinCEN 314 requirment. |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No: No; Low: Moderate; Low: Moderate; Low: Moderate; Low: Low; Low: Moderate | 12+ Months | Planning | Moderate | Financial Impact - Moderate Customer IMpact- Low Regulatory Impact- Moderate Reputational Impact- Moderate |  | Technology; (IT Change) | 1/1/2024 | 12/31/2026 |  | 02/11/2026 | On Hold | NA | NA | No | Global Connectivity;Simplification | 1 | Missing |  | 2025-01-02 | 2025-12-31 | 2026-08-30 | 2025-01-16 | 2025-01-27 | A | A | [5 empty] | $ 0 | Non Active | Waterfall | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold because of SHUSA Top Management request. |  |  |  | Yes |  |  | No |  |  | FCC/KYC/AMC |  | 31108
72144 | 3262 | Phoenix (BSI) | BSI_Technology |  |  | IT for IT | Joshua De Leon | Approved |  | Joshua De Leon | Jose Luis Martinez Avial | Elizabeth Noda | Mercedes Sastre Gallego | None | None | BSI | Current T24 solution is obsolete and requires upgrading current version to the latest release version. | Technology | Jose Oliveros |  | Yes | IT Projects | L: > $2M | No: No; Low: Critical; Low: High; Low: Moderate; Low: Very Low; Low: Moderate | 12+ Months | Execution | Moderate | d | BCO approved risk assessment on 02/11/2026. | Technology; (IT Change) | 3/1/2021 | 12/31/2025 |  | 9/4/2026 | Green | NA | NA | No | Must-Do | 1 | Approved | 02/11/2026 | 2021-03-15 | 2027-12-10 | 2026-09-04 | 2025-01-17 | 2025-01-17 | B3P | B3P | Increase | Moderate | Low | High | N/A | $ 0 | Active | Waterfall | No | Green |  |  | Amber | Issue: some internal resources planned to work on Phoenix project are being assigned to other tasks (BAU support or other projects), therefore miami specific developments are a bit behind schedule. Ri | 11/30/2027 | Green |  |  | Amber | New changes / projects are still being implemented under R11, and will have to be replicated in R25, increasing Phoenix scope. Also new features are accepted to be implemented in R25 (example: NDF new | 2/28/2027 | Green |  |  | On track. Geneva went live on August 10th. System stabilization on-going and EoM executed with no issues. Miami release: build phase is about to resume on Oct. 1st (working on detailed plan and resources allocation). In parallel, team continues with SIT testing execution and UAT environment set-up. |  |  |  | Yes |  |  | No |  |  |  | 1937 | 31103
31898 | 31898 | Plan Basico Updates | BSI_Risk |  |  | N/A | Joshua De Leon | Approved |  | Jimena Perez-Castro | Bonilla, Rafael | Jose Maria Lafora | Carlos de Lemos |  |  | BSI | This initiative proposes updates to the existing Plan Basico suitability limits to simplify and optimize the fiduciary control framework. Certain overlapping limits (e.g., Emerging Markets, Complexity, Currency Mismatch) will be removed or consolidated, while the Illiquidity limit will be enhanced. The Plan Basico algorithm will also be updated to better align client financial knowledge with advisory eligibility for complex products. These changes require updates to the 360 tool, alerts, disclosures, reporting, and client communications. | Risk;CommercialREVF | N/A, Non-IT project |  |  | Non-IT Projects | S: < $500k |  | No | No | Very Low | Low | Low | Low | Low | Low | Low | Low | Low | Very Low | No | 0-6 Months | Execution | Low | this initiative is assessed as Low overall across all dimensions. The Plan Basico updates affect suitability limits, 360 tool logic, alerts, disclosures, reporting and client communications, creating limited regulatory/compliance, IT, strategic, reputational/customer and people-adoption considerations. The impact is not higher because the changes optimize an existing fiduciary-control framework rather than introducing a new product, major platform or broad operating model change. |  | BusinessActivity; | 1/5/2026 | 4/30/2026 |  |  |  | NA | NA | No | Simplification;Transformation | 0 | Missing | [5 empty] | 2026-03-11 | L | L | [5 empty] | $ 0 | Active | Waterfall | No | [19 empty] | No |  |  | No |  |  | Risk |  | 31898
72158 | 3500 | Plata | BSI_Strategy |  |  | None |  | Approved | 02/10/2025 02:31:54 PM | Joshua De Leon | Ximena Ardila | Jose Maria Lafora | NA | None | None | BSI | BSI is looking to open an office in Mexico | Auto; |  | Yes | Yes | IT Projects | L: > $2M | No | No | Yes | Low | Low | N/A | N/A | N/A | N/A | Low | N/A | Low | Low | No | 6-12 Months |  | Low | ss |  | Technology;BusinessActivity; | 03/03/2025 | 12/31/2025 |  | 02/20/2025 | On Hold | NA | NA | No | Profitable Growth; | 1 | Missing |  |  |  |  | 2025-02-10 09:52 | 2025-02-10 14:32 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | Head of Strategy has requested to cancel this project. The Budget will not be allocated to another project. |  |  |  | No |  |  | No
72828 | 3668 | Plata Advisory Office Mx | BSI_Strategy |  | No | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Ximena Ardila | Jose Maria Lafora | Cristian Krossler |  |  | BSI | BSI is looking to open an Advisory office in Mexico. |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No: Yes; No: No; Low: Low; Low: Moderate; Low: Moderate; Low: Low; Low: Moderate | 6-12 Months | Closed | High | Financial Impact- Low Customer Impact- Low Regulatory Impact- Low Reputational Impact - Low | BCO approved risk assessment on 07/11/2025. | Strategy;NPBA;Technology; (IT Change) | 1/1/2025 | 12/12/2025 | 9/2/2026 5:36:41 PM | 03/05/2026 | Complete | NA | NA | Yes | Profitable Growth | 1 | Missing |  |  |  |  | 2025-04-02 | 2025-04-02 | B3P | B3P | [5 empty] | $ 0 | Non Active |  | Yes | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | Establishment of a licensed investment advisory office in Mexico as a subsidiary of BSI. |  |  |  | No |  |  | No
72777 | 3517 | Posit - Python | BSI_Technology |  | No |  |  | Approved | 02/20/2025 11:31:23 AM | Joshua De Leon | Jose Oliveros | Elizabeth Noda | NA |  |  | BSI | BSI is initiating a project to adopt an Enterprise Data Platform compatible with Python and R, aimed at enhancing financial data analysis and decision-making through Machine Learning. This aligns with BSI’s strategic goals of digital transformation, operational efficiency, and data-driven insights, promising reduced errors and improved investment strategies. | Technology; |  | No | Yes | IT Projects | S: < $500k | Yes | No | Yes | Low | Low | N/A | N/A | N/A | N/A | Low | N/A | Very Low | Low | No | 6-12 Months |  | Low | n |  | Technology; | 10/01/2024 | 06/30/2025 | 11/20/2025 10:34:16 PM | 08/11/2025 | Complete | NA | NA | No | Transformation; | 1 | Approved | 05/09/2025 |  |  |  | 2025-02-19 15:16 | 2025-02-20 11:31 | ABC | NA | Stable | Low | Low |  | N/A | $ 0 | Non Active |  | No | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | We deployed Posit in the BSI infrastructure successfully. All benefits and functionalities were achived for the business by being able to use Python. |  |  |  | No |  |  | No
72962 | 3747 | PRIVA | BSI_Products and Investments |  |  | Products |  | Approved | 07/15/2025 01:10:12 PM | Nathalie Brandon | Ivan Howard | Belen Monzon | NA |  |  | BSI | New Irish Collective Asset Vehicle for Alternative Investments with launch of new fund Spruceview Select LMN US Buout Access Fund I | Legal; |  |  | No | Non-IT Projects | S: < $500k | No | No | Yes | Moderate | High | N/A | N/A | N/A | N/A | Low | N/A | Low | Low | No | 0-6 Months |  | Moderate | Alternative investment product has the potential to bring higher level of scrutiny from the regulators in terms of fiduciary and legal risk. Our goal is to align product distribution under this initiative. | This is the 8th year offering alternative investments funds. BSI has implemented robust controls on sales process, product monitoring, and legal disclosures. Change on ICAV to PRIVA will not have noticeable difference on the offering of products to our clientele. | NPBA; | 07/11/2025 | 09/01/2025 | 11/3/2025 9:12:19 PM | 10/27/2025 | Complete | NA | NA | Yes | Must-Do; | 1 | Missing |  |  |  |  | 2025-07-15 13:10 | 2025-07-15 13:10 | H | NA | [5 empty] | NA | Non Active |  | No | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | N/A |  |  | Went to NPBA friday 9/26 Got PTO on 10/20 |  |  |  | No |  |  | No
32371 | 32371 | Project Mouro Capital Access Fund | BSI_Products and Investments |  |  | Products | Joshua De Leon | Approved |  | Igor Ugarte | Bueso-Inchausti Aguirre, Alvaro | Belen Monzon | Igor Ugarte |  |  | BSI | The Alternative Investments Team is presenting for approval the PRVA sub fund that will invest in Mouro Parallel SCSp, SICAV-RAIF (“MC II” or “The Fund”), a close-ended venture capital fund investing at the intersection of technology and finance with a focus on early-to-growth stag fintech and enterprise software businesses across a variety of industries and geographies. The Fund carried out its first close in July 2025 with a $300Mn commitment from Banco Santander, with the possibility of increasing its commitment to $400Mn. The funds aim to team up with world-class entrepreneurs redefining the future of the financial services industry investing primarily across North America, Europe and Latin America. The Fund targets to carry out 30-35 investments through $3-15Mn check size with a preference to lead and invest in Seed to Series C rounds. | Risk;Legal | N/A, Non-IT project |  |  | Non-IT Projects | S: < $500k |  | No | No | Low | Moderate | Low | Very Low | Low | Low | Moderate | Very Low | N/A | N/A | No | 0-6 Months | Planning | Moderate | Adding a new fund to the portfolio. All associated processes will remain the same. |  | NPBA; | 7/1/2026 | 9/30/2026 |  | 9/24/2026 | On Hold | NA | NA | Yes | Profitable Growth | 1 | Approved | 08/10/2026 | 2026-07-01 | 2026-11-13 | 2026-09-09 | 2026-07-01 | 2026-07-01 | H | H | Stable | Moderate | Low |  | N/A | NA | Non Active | Waterfall | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | Initiative put on hold until business clarifies scope |  |  |  | No |  |  | No |  |  | Savings and Investments |  | 32371
31910 | 31910 | Project Obsidian | BSI_Products and Investments |  |  | Products | Joshua De Leon | Approved |  | Igor Ugarte | Bueso-Inchausti Aguirre, Alvaro | Belen Monzon | Igor Ugarte |  |  | BSI | The proposed co-investment will be offered with Banco Santander International investors participating in an opportunity to acquire a portfolio representing USD 1455.5 Million across 75 funds and 46 GPs. StepStone is indicating USD 146.4 Mn of Project Obsidian to underlying co-investors like Santander. | Risk;Legal | N/A, Non-IT project |  |  | Non-IT Projects | S: < $500k |  | No | No | Low | Low | Low | Very Low | Low | Low | Low | Very Low | N/A | N/A | No | 0-6 Months | Execution | Low | Adding a new fund to the portfolio. All associated processes will remain the same. |  | NPBA; | 5/1/2026 | 6/30/2026 |  |  |  | NA | NA | Yes | Profitable Growth | 0 | Approved | 09/29/2026 |  |  |  |  | 2026-04-17 | L | L | Stable | Moderate | Low |  | N/A | $ 0 | Active | Waterfall | No | [19 empty] | No |  |  | No |  |  | Savings and Investments |  | 31910
30578 | 30578 | QA Efficiency imporvement and automation | BSI_Risk |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Bonilla, Rafael | Jose Maria Lafora | Carlos de Lemos | None | None | BSI | mplementation of QA process within APPIAN onbarding workflow. This will allow the team to better analize cases required and also automate some of the features of the program |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k |  | No | No | Very Low | Moderate | Low | Low | Low | Very Low | Very Low | Low | Very Low | Very Low | Yes | 12+ Months | Board Approved | Moderate | this initiative is assessed as moderate overall. Regulatory/Compliance is Moderate because the QA automation supports onboarding review activities connected to regulatory/customer due diligence controls, but it does not introduce a major new regulatory obligation. Financial, Innovation and Reputational/Customer impacts are Very Low, while Third-Party, IT, Strategic/Business and People/Change Adoption are Low due to limited Appian workflow changes and manageable internal adoption requirements. |  | Technology; (IT Change) | 1/1/2026 | 12/31/2028 |  | 01/28/2026 | Not Started | NA | NA | No | Simplification;Transformation | 0 | Missing |  |  |  |  | 2026-01-08 | 2026-01-09 | A | A | [5 empty] | $ 0 | Non Active |  | No | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  |  | Yes |  |  | No |  |  | Risk
513 | NA | Real Estate Co-Investment fund | BSI_Products and Investments |  |  | Products | N/A | Saved |  | Igor Ugarte |  | Belen Monzon | NA |  |  | BSI |  |  |  |  | No | Non-IT Projects |  | No: No; Yes: No; Low: N/A; Low: N/A; No: Yes | 0-6 Months |  |  |  |  | NPBA; | 10/1/2026 | 3/31/2027 |  |  |  | NA | NA | No | Profitable Growth | 0 | Missing | [6 empty] | N/A | NA | [5 empty] | NA | Non Active |  | NA | [19 empty] | No |  |  | No
30559 | 30559 | Record Retention | BSI_Operations |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Maria Teresa Del Cerro | Jose Maria Lafora | John Pendas | None | NO | BSI | Creation of an office to coordinate the record retention activities |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k |  | No | No | Low | Low | Moderate | Low | Moderate | Very Low | Very Low | Moderate | Very Low | Very Low | No | 0-6 Months | Board Approved | Moderate | this initiative is assessed as Moderate overall. Financial and Regulatory/Compliance impacts are Low because the budget is <$500k and record retention obligations are managed through an internal coordination office rather than a major new regulatory program. Third-Party Dependency, Strategic/Business Impact and People/Change Adoption are Moderate because record retention requires coordinated governance, process ownership and adoption across responsible teams. IT, Innovation and Reputational/Customer impacts are Low to Very Low due to limited system and external customer exposure. |  | BusinessActivity;Technology; (IT Change) | 7/1/2026 | 12/31/2026 |  | 01/28/2026 | Not Started | NA | NA | No | Simplification | 0 | Missing |  |  |  |  | 2026-01-08 | 2026-01-08 | A | A | [5 empty] | $ 0 | Non Active |  | No | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  |  | Yes |  |  | No |  |  | Risk
72150 | 3259 | Record Retention Office | BSI_Operations |  |  | None |  | Approved | 01/23/2025 04:25:58 PM | Joshua De Leon | Javier Rodriguez Hergueta | John Pendas | NA | None | None | BSI | Create the Record Management Office (RMO) in order to align with the Record Management Policy and standard. The RMO will be responsible for managing the lifecycle of records from creation and maintenance to storage and disposal - ensuring compliance with legal, regulatory, and organizational requirements. It will serve as the central authority to standardize processes, enhance operational efficiency, and mitigate risks associated with poor record management. | Technology;Operations; |  | Yes | Yes | IT Projects | S: < $500k | Yes | No | Yes | Moderate | Moderate | N/A | N/A | N/A | N/A | Moderate | N/A | Moderate | Low | No | 6-12 Months |  | Moderate | n |  | Technology;BusinessActivity; | 01/01/2025 | 11/26/2025 |  | 02/14/2025 | On Hold | NA | NA | No | Simplification; | 1 | Missing |  |  |  |  | 2025-01-23 16:19 | 2025-01-23 16:26 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | Project to be canceled |  |  |  | No |  |  | No
31422 | 31422 | Regulatory Documentation- ETF feed | BSI_Products and Investments |  | No | Products | Joshua De Leon | Approved |  | Carlos de Lemos | Ricardo Garcia-Marques | Belen Monzon | Carlos de Lemos | 005056BCB79A1EDFA792BEDF14642663 | Delivery Information Structured Notes, Alternative Funds and ETFs | BSI | As part of regulatory requirements to provide customers with documentation related to investments (Prospectus, fact sheet), we have implemented two different channels for Mutual Funds (Direct feed from All Funds), Structured notes and private equity (direct upload of document in T24). We are now working on implementing feature for ETFs via a direct feed from Euroclear. This will be a similar process as the one implemented for mutual funds. |  | Jose Oliveros |  | No | IT Projects | S: < $500k | Yes | No | Yes | Low | Moderate | Low | Very Low | Low | Low | Moderate | Low | Moderate | Very Low | No | 0-6 Months | Closed | Moderate | this initiative is assessed as Moderate overall. Regulatory/Compliance and Reputational/Customer impacts are Moderate because the Euroclear feed supports required delivery of ETF documentation to customers and reduces manual error risk. Financial, Third-Party, Strategic/Business, Innovation and People impacts are Low due to manageable cost, feed dependency and process adoption, while IT impact is Very Low because the work follows an already established documentation-feed approach. |  | BusinessActivity;Technology; (IT Change) | 1/26/2026 | 12/31/2026 | 9/2/2026 5:36:44 PM | 6/18/2026 | Complete | NA | NA | No | Must-Do | 1 | Approved | 03/10/2026 |  |  |  | 2026-01-16 | 2026-01-26 | B3P | B3P | Decrease | Moderate | Low |  | N/A | $ 0 | Non Active |  | No | Completed |  |  | Completed |  |  | Completed |  |  | Completed |  |  | Completed |  |  | Project completed |  |  |  | No |  |  | No |  |  | Savings and Investments
72139 | 3526 | RPA (Robotic Process Automation) | BSI_Risk |  |  | None |  | Approved | 02/21/2025 02:39:22 PM | Joshua De Leon | Alfredo Aguila | Jose Maria Lafora | NA | None | None | BSI | Implementation of Robots Process Automation to reduce manual workload and generate automated alerts to the compliance risk department. | Technology;Risk; |  | Yes | Yes | IT Projects | M: $500k - $2M | No | No | Yes | Moderate | Very Low | N/A | N/A | N/A | N/A | Very Low | N/A | Very Low | Very Low | Yes | 12+ Months |  | Moderate | s |  | Technology;BusinessActivity; | 01/01/2024 | 12/31/2025 |  | 03/28/2025 | On Hold | NA | NA | No | Simplification;Transformation; | 0 | Missing |  |  |  |  | 2025-02-10 09:56 | 2025-02-21 14:39 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | Project set to be canceled |  |  |  | No |  |  | No
71048 | 3027 | RPA Robot Process Automation | BSI |  |  |  |  | Approved | 11/07/2024 01:57:27 PM | Ana Cabezuelo | Alfredo Aguila | Mourino, Mario | NA |  |  | BSI | Implementation of the RPA Technology for automating different activities. | Technology;Risk; |  | Yes | Yes | IT Projects | S: < $500k | Yes | No | Yes | Low | Moderate | N/A | N/A | N/A | N/A | Moderate | N/A | Moderate | Moderate | No | 6-12 Months |  | Moderate | There are not change in the way we do things. This is just to automate with RPAs. |  | Technology; | 01/02/2025 | 12/30/2025 | 11/22/2024 9:59:29 PM | 11/20/2024 | Complete | NA | NA | No | Simplification; | 1 | Approved | 11/08/2024 |  |  |  | 2024-11-07 13:53 | 2024-11-07 13:57 | ABC | NA | Decrease | High | Low |  | N/A | $ 0 | Non Active |  | No | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | Bla, bla, bla, bla, bla, |  |  |  | No |  |  | No
73020 | 3767 | Rundeck | BSI_Technology |  |  | N/A | Joshua De Leon | Approved |  | Eric Linares | David Calmaestra | Elizabeth Noda | Eric Linares |  |  | BSI | This project introduces Rundeck, an open-source automation tool, to automate current ETL (Extract, Transform, Load) processes that are currently handled via cron jobs and manual script executions on Linux servers. There is no existing dedicated application for these tasks. The proposed solution will automate file movement and processing, trigger Close of Business (COB) operations, and support multiple triggering methods: event-based (e.g., file arrival), scheduled, and manual. |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No: No; Low: Moderate; Low: Very Low; Low: Moderate; Low: Moderate; Low: Very Low | 12+ Months | Planning | Low | If runing the COB fails, it will impact opening the bank the following day impacting Financial and Customer. | BCO approved risk assessment on 08/27/2025. | Technology; (IT Change) | 8/19/2025 | 4/30/2026 |  | 8/26/2026 | Green | NA | NA | No | Simplification;Transformation | 1 | Approved | 08/31/2026 | 2025-08-01 | 2026-11-10 | 2026-08-30 | 2025-08-21 | 2025-08-21 | CND | CND | Decrease | Moderate | Low |  | N/A | $ 0 | Active | Waterfall | No | Green |  |  | Green |  |  | Green |  |  | Green |  |  | Green |  |  | The Rundeck Project has been created. |  |  |  | No |  |  | No | Phased Implementation | Phased rollout of Rundeck automation, incrementally onboarding existing ETL and Close of Business processes. This approach minimizes operational risk and allows validation before expanding automation scope. | Cloud infrastructure and common IT Run |  | 31242
72038 | 3271 | SAP Hana - Looking Ahead | BSI_Procurement |  |  |  |  | Approved | 01/27/2025 04:06:43 PM | Joshua De Leon | Eloina Franco-Espinosa | Jose Maria Lafora | NA |  |  | BSI | The Looking Ahead aim is to define and implement a new Spend Management Model (End to End process,operating model & Technology) that increase visibility, insight generation and control while allows business to focus on execute their strategy. The current solution is outdated. | Finance;Technology; |  | Yes | Yes | IT Projects | M: $500k - $2M | No | No | Yes | Moderate | Low | N/A | N/A | N/A | N/A | Very Low | N/A | Very Low | Very Low | Yes | 12+ Months |  | Moderate | Financial Impact- Moderate Customer Impact- Very Low Regulatory Impact - Low Reputational Impact- Very Low |  | Technology; | 04/01/2023 | 04/30/2025 | 8/27/2025 3:19:15 PM | 07/15/2025 | Complete | NA | NA | No | Global Connectivity; | 1 | Approved | 03/28/2023 |  |  |  | 2025-01-16 11:17 | 2025-01-27 16:07 | ABC | NA | Stable | Critical | Critical | Moderate | N/A | $ 0 | Non Active |  | No | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | Complete |  |  | Project is complete and live in production |  |  |  | No |  |  | No
31043 | 31043 | SAP Payment Modification Process & Other Developments for BSI | BSI_Finance |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Julio Leanez | Jose Maria Lafora | Julio Leanez | None | None | BSI | Cost Control |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k |  | No | No | Low | Very Low | Moderate | Moderate | Moderate | Low | Very Low | Very Low | Very Low | Very Low | No | 6 - 12 months | Board Approved | Moderate | this initiative is assessed as Moderate overall. Financial and Innovation/Emerging Risk impacts are Low because the work supports cost control and process improvements without a material budget or novel technology exposure. Third-Party Dependency, Information Technology and Strategic/Business Impact are Moderate because SAP/payment-process developments introduce manageable vendor/system dependency and support finance control objectives. Regulatory, Reputational/Customer and People impacts remain Very Low due to limited external or adoption exposure. |  | Technology; (IT Change) | 2/16/2026 | 12/15/2026 |  | 01/28/2026 | Not Started | NA | NA | No | Simplification | 0 | Missing |  |  |  |  | 2026-01-08 | 2026-01-09 | A | A | [5 empty] | $ 0 | Non Active |  | No | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  |  | Yes |  |  | No |  |  | MIS (all financial and non-financial information)
30558 | 30558 | Security platform master | BSI_Operations |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Marcel Garcia | John Pendas | Ana Cabezuelo | None | NO | BSI | R1 - Implement an interim Appian/API enhancement to perform real-time sanction validation for securities involved in Transfer IN requests. The solution will allow Appian to check the sanction status of securities available in the bank’s Security Master and request real-time enrichment from Bloomberg PolarLake when the security is not currently maintained due to lack of position. R2 - Replace the current Bloomberg PolarLake Security Master platform with a new vendor solution, including the required integrations, data migration, and transition of security reference data processes to the target-state platform. | Operations;Technology;Finance;Risk | Jose Oliveros |  | Yes | IT Projects | S: < $500k | Yes | No | Yes | Low | Low | High | High | Moderate | Moderate | Low | Moderate | Low | Low | No | 0-6 Months | Planning | High | this initiative is assessed as High overall, with targeted High drivers. Financial and regulatory impacts are Low given the <$500k budget and continued use of existing controls; however, Third-Party Dependency and Information Technology are High because replacing BPL for security-master data quality creates significant vendor/system reliance and delivery risk. Strategic/Business, Innovation/Emerging Risk and People/Change Adoption are Moderate due to the importance of security-master controls, a new platform/process, and user adoption needs. |  | Technology; (IT Change) | 7/1/2026 | 12/31/2026 |  | 9/30/2026 | Green | NA | NA | No | Must-Do | 1 | Approved | 06/25/2026 | 2025-06-19 | 2027-12-31 | 2026-08-29 | 2026-01-08 | 2026-01-08 | B3P | B3P | Stable | High | Low |  | N/A | $ 0 | Active | Waterfall | Yes | Green |  |  | Green |  |  | Amber | Scheedule amber because of new UAT will be needed. | 10/30/2026 | Green |  |  | Green |  |  | The UATs are being conducted but something was not complying with the requirement and UAT will be repeated next week. |  |  |  | Yes |  |  | No |  |  | Savings and Investments | 3341 | 30558
72149 | 3599 | Security Sanctions | BSI_Risk |  |  | None |  | Approved | 03/11/2025 10:00:02 AM | Joshua De Leon | Alfredo Aguila | Jose Maria Lafora | NA | None | None | BSI | BSI will be uplifting the Security Sanctions process. | Technology;Risk;Legal; |  | Yes | Yes | IT Projects | M: $500k - $2M | Yes | No | Yes | Low | Moderate | N/A | N/A | N/A | N/A | Low | N/A | Low | Low | No | 6-12 Months |  | Moderate | s |  | Technology;BusinessActivity; | 09/01/2025 | 12/31/2025 |  | 03/21/2025 | On Hold | NA | NA | No | Must-Do; | 0 | Missing |  |  |  |  | 2025-02-10 09:54 | 2025-03-11 10:00 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | Project was requested to be canceled by the executitve sponsor as there is other projects within the portfolio that require more priority. |  |  |  | No |  |  | No
31885 | 31885 | SICAV Bel Canto Trovatore | BSI_Products and Investments |  |  | Products | Joshua De Leon | Approved |  | Igor Ugarte | Alejandro Uriarte | Belen Monzon | Igor Ugarte |  |  | BSI | Sub-Fund aims to generate a return that aligns with the performance of US T-Bill yield curve by investing in USD denominated fixed income securities. | Risk | N/A, Non-IT project |  |  | Non-IT Projects | S: < $500k | Yes | No | Yes | Very Low | Very Low | Low | Very Low | Very Low | Very Low | Low | Very Low | Low | Very Low | No | 0-6 Months | Execution | Low | this initiative is assessed as Low overall. Financial, Regulatory/Compliance, IT, Strategic/Business, Innovation and People impacts are Very Low because the sub-fund/investment objective does not materially change internal operations or technology. Third-Party Dependency and Reputational/Customer impacts are Low because the product has external investment and customer-facing characteristics, but the associated risks appear manageable through existing product governance. |  | BusinessActivity; | 2/2/2026 | 2/27/2026 |  |  |  | NA | NA | No | Profitable Growth | 0 | Approved | 07/23/2026 |  |  |  | 2026-01-29 | 2026-02-03 | L | L | Stable | Low | Low |  | N/A | $ 0 | Active | Waterfall | No | [19 empty] | No |  |  | No |  |  | Savings and Investments |  | 31885
73066 | 3802 | SICAV CUST CHANGE (JPM-CACEIS) | BSI_Products and Investments |  |  | Products | Joshua De Leon | Approved |  | Alfonso Camano | Manuel Perez Duro | Cynthia Morzan | Alfonso Camano |  |  | BSI | Santander Asset Management is migrating all SICAV and FUNDS Custodian from JPM to CACEIS. This includes the funds where BSI is the delegated investment manager. | Technology;Operations | Jose Oliveros |  | No | IT Projects | S: < $500k | No: No; Low: Low; Low: Low; Low: Low; Low: Low; Low: Low | 0-6 Months | Canceled | Low | . |  | Strategy;Technology; (IT Change) | 10/7/2025 | 11/17/2025 |  | 8/18/2026 | On Hold | NA | NA | No | Must-Do | 0 | Missing |  |  |  |  | 2025-10-09 | 2025-10-10 | B3P | B3P | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | BSI has decided to cancel this project, as the initiative has been identified as a BAU by the System Development Director. |  |  |  | No |  |  | No
31640 | 31640 | Tableau migration to cloud | BSI_Technology |  |  | IT for IT | Joshua De Leon | Approved |  | David Calmaestra | David Calmaestra | Elizabeth Noda | Raul Fort | ID005056BCB79A1FD083E3528C73494665 | 2025 BSI - ISAR Design Deficiencies - Tableau | BSI | Migrate the current on-premises tableau infrastructure to cloud and decomision the current infrastucture as it currently has security vulnerabilities | Technology | Jose Oliveros |  | No | IT Projects | S: < $500k | Yes | No | Yes | Low | Low |  |  |  |  | Very Low |  | N/A | N/A | No | 0-6 Months | Planning | Low | Financial: 280k Customer: no customer facing Regulatory: there is a couple of dashboards which tracks regulatory kpis Reputational: no customer facing, dashboard are all informational |  | Technology; (IT Change) | 2/16/2026 | 5/29/2026 |  | 7/29/2026 | Green | NA | NA | No | Simplification | 1 | Approved | 05/21/2026 | 2025-11-28 | 2026-10-26 | 2026-08-29 | 2026-02-10 | 2026-02-10 | CND | CND | Increase | High | Low | Moderate | N/A | $ 0 | Active | Waterfall | No | Green |  |  | Green |  |  | Green |  |  | Green |  |  | Green |  |  | RAG status of the project is currently in green. Working on artifacts for Gate 5 |  |  |  | No |  |  | No |  |  | Data / AI | 8028 | 31640
30577 | 30577 | Technology Support for Cost Management (Data Mart) | BSI_Finance |  |  | N/A | Joshua De Leon | Approved |  | Joshua De Leon | Garay Gallastegui Augusto Felix | Jose Maria Lafora | Julio Leanez | None | None | BSI | Expense Management Optimization |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k | No | No | Yes | Moderate | Very Low | Low | Moderate | Moderate | Low | Very Low | Very Low | Very Low | Very Low | No | 6 - 12 months | Board Approved | Moderate | this initiative is assessed as Moderate in selected areas and Low overall. Financial impact is Moderate because the data mart supports expense management and cost allocation decisions, even though the budget remains manageable. Information Technology and Strategic/Business Impact are Moderate because the change requires system/data integration and supports cost-management strategy. Regulatory, Reputational/Customer and People impacts are Very Low, with only Low vendor/innovation exposure, because this is an internal finance analytics enhancement. |  | Technology; (IT Change) | 1/15/2026 | 12/15/2026 |  | 01/28/2026 | Not Started | NA | NA | No | Simplification | 0 | Missing |  |  |  |  | 2026-01-08 | 2026-01-09 | B3P | B3P | [5 empty] | $ 0 | Non Active |  | No | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  | Not Started |  |  |  | Yes |  |  | No |  |  | MIS (all financial and non-financial information)
31784 | 31784 | TIIE Mexico | BSI_Commercial |  |  | N/A | Joshua De Leon | Approved |  | Jose Lafarga | Jose Lafarga | Carolina Alvarez | Jose Lafarga |  |  | BSI | Given the frequently requirement of Mexican clients to use the Interbank Equilibrium Interest Rate (TIIE) as reference rate for floating rate loans denominated in MXN, we are looking to cover this customer need in BSI by offering TIIE as reference index in addition to our current offer in MXN Base Rate. TIIE is a public rate calculated and published by the Mexican Central Bank (Banco de Mexico – Banxico) daily. | CommercialREVF;Risk;Legal;Technology;Operations;Finance | N/A, Non-IT project |  |  | Non-IT Projects | S: < $500k |  | No | No | Low | Low | Low | Low | Low | Low | Low | Low | N/A | N/A | No | 0-6 Months | Closed | Low | The proposed change consists of adding TIIE as an additional reference rate for MXN floating-rate loans. TIIE is a publicly available benchmark published daily by Banco de México. This change does not introduce a new product or modify the existing credit structure, risk profile, or client eligibility criteria. Low – Financial Risk: The impact is limited, as this is only an additional reference rate option. It does not affect revenue streams, pricing strategy, or balance sheet exposure, since only the reference rate used to calculate interest is changing, not the underlying exposure or risk. Any interest rate exposure arising from the use of TIIE would be expected to be managed within existing hedging frameworks, as part of BAU activities, subject to validation by the relevant Treasury and Risk teams. Low – Regulatory and Compliance Risk: TIIE is a widely recognized benchmark in the Mexican market and its use is consistent with standard market practice. No new regulatory approvals or changes to existing frameworks are required, and all current controls (KYC, AML, and product governance) remain in place. Legal documentation will need to be reviewed and updated, and relevant system fields will need to be updated to support the new reference rate. Low – Customer and Reputational Risk: The change is client-driven and aligns with local market standards and expectations. It does not negatively affect customers or increase complexity. There is a limited risk related to disclosure or client understanding; however, this is mitigated through internal processes and clear communication of terms and conditions. Overall Conclusion: The financial, regulatory, compliance, and reputational risks are considered low, as this change does not introduce a new product but only an additional benchmark rate. Existing controls and BAU processes will continue to apply, ensuring that risks are appropriately managed. |  | BusinessActivity; | 3/12/2026 | 8/31/2026 |  |  |  | NA | NA | No | Profitable Growth | 0 | Missing | [5 empty] | 2026-03-17 | L | L | [5 empty] | $ 0 | Non Active |  | No | [19 empty] | No |  |  | No |  |  | Customer Interactions
72162 | 3268 | TOMs (Robotics & Appian) | BSI_Finance |  |  | None |  | Approved | 01/27/2025 03:58:08 PM | Joshua De Leon | Eloina Franco-Espinosa | Jose Maria Lafora | NA | None | None | BSI | Automation thorugh the implementation of RPA Technology of 1 process (TPG Reconciliation) and 3 sub-processes (Duco Reconciliation, Custodian Reconcilation and BS Nostros Account Reconciliation) in the Controllership Area | Finance;Technology; |  | Yes | Yes | IT Projects | S: < $500k | Yes | No | Yes | Low | Low | N/A | N/A | N/A | N/A | Low | N/A | Low | Low | No | 6-12 Months |  | Low | n |  | Technology;BusinessActivity; | 02/03/2025 | 12/31/2025 |  | 05/08/2025 | On Hold | NA | NA | No | Simplification;Transformation; | 1 | Missing |  |  |  |  | 2025-01-27 08:13 | 2025-01-27 15:58 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | Project will be develop in another technology (Tableau) as the RPA technology to be used by BSI will change (from Uipath to Appian RPA Technology) This specific project will be canceled. |  |  |  | No |  |  | No
72735 | 3373 | Transaction Monitoring ECS | BSI_Risk |  |  | N/A | Joshua De Leon | Approved |  |  | Maria Martinez | Jose Maria Lafora | Ana Cabezuelo |  |  | BSI | The current Transaction Monitoring (TM) tool Assist is going to be deprecated. The current vendor will stop providing service by April 2026. We need to implement a new TM tool before end of year because we need at least three months since we are ready to go live to get the Model Risk Management Approvals. We are leveraging on a current Application broadening the capabilities of the currently in use. This capabilities, in addition to cover the need of having the TM tool replaced will bring additional capabilities that will help to simplify and do more efficient our current TM process. |  | Jose Oliveros |  | Yes | IT Projects | S: < $500k | Yes: No; No: No; Low: Low; Low: Critical; Low: High; Low: Low; Low: High | 6-12 Months | Execution | Moderate | Regulatory & Risk mitigant Transaction Monitoring is a Mandatory process that requires a tool. | BCO approved risk assessment on 03/14/2025. | Regulatory;Technology; (IT Change) | 2/4/2025 | 12/31/2025 |  | 9/30/2026 | Amber | NA | NA | No | Simplification | 1 | Missing |  | 2024-10-30 | 2027-05-17 | 2026-08-30 | 2025-02-20 | 2025-02-20 | B3P | B3P | [5 empty] | $ 0 | Active | Waterfall | No | Green |  |  | Amber | Many MRM deliveries are needed. MRM resource transitioning to SHUSA and Knowledge transfer happening in parallel to the MRM package preparation. | 11/30/2026 | Amber | Many MRM deliveries are needed. We will deliver the MRM package on time but probably they will request additional information. | 11/30/2026 | Green |  |  | Green |  |  | Finalizing the deliveries for MRM still Amber due to the complexity and close dates. |  |  |  | Yes |  |  | No |  |  |  | 3293 | 31234
73077 | 3814 | US WEALTH - SACA | BSI_Strategy |  |  | N/A | Joshua De Leon | Approved |  | Szemzo, Favia | Ximena Ardila | Jose Maria Lafora | Diego Perez Fleta |  |  | BSI | As part of the US Wealth project, offer SACA lending capabilities, with BSI being the lender. This will require a workflow developed with Appian. | Risk;Operations | Jose Oliveros |  | Yes | IT Projects | S: < $500k | Yes: Yes; No: No; Yes: Yes; Low: Low; Low: Low; Low: Low; Low: Low; Low: Low | 0-6 Months | Execution | Moderate | . | BCO approved risk assessment on 01/16/2026. | NPBA;Technology; (IT Change) | 10/23/2025 | 8/31/2026 |  | 05/20/2026 | On Hold | NA | NA | Yes | Must-Do | 1 | Approved | 03/19/2026 | 2025-01-02 | 2026-08-31 | 2026-08-30 | 2025-10-23 | 2025-10-30 | A | A | Increase | High | Low | Moderate | N/A | $ 0 | Non Active | Waterfall | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  |  | No |  |  | No |  |  | Risk | 2062, 1937, 3506 | 31247
72142 | 3619 | Web & App Backend Upgrade | BSI_Commercial |  |  | None |  | Approved | 03/17/2025 11:15:40 AM | Joshua De Leon | Eugenio Alvarez | Maria Fernanda Lopez | NA | None | None | BSI | Current Ebanking Application is outdated and has opportunities to enhance usability by rebuilding and/or substitute for new and more robust, scalable and friendly Application. | Technology; |  | Yes | Yes | IT Projects | M: $500k - $2M | Yes | No | Yes | Very Low | Very Low | N/A | N/A | N/A | N/A | Low | N/A | Low | Very Low | No | 6-12 Months |  | Low | n |  | Technology; | 04/01/2025 | 12/31/2025 |  | 01/23/2026 | On Hold | NA | NA | No | Transformation; | 1 | Missing |  |  |  |  | 2025-02-21 14:43 | 2025-03-17 11:16 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | This project was decided to be canceled by managment due to budget re-prioritization |  |  |  | No |  |  | No
72030 | 3621 | Web New Functionalities | BSI_Commercial |  |  |  |  | Approved | 03/17/2025 11:13:21 AM | Joshua De Leon | Eugenio Alvarez | Maria Fernanda Lopez | NA |  |  | BSI | Current Web Application is outdated and has opportunities to enhance usability by rebuilding and/or substitute for new and more robust, scalable and friendly Application. | CommercialREVF;Technology; |  | Yes | Yes | IT Projects | M: $500k - $2M | Yes | No | Yes | Very Low | Very Low | N/A | N/A | N/A | N/A | Low | N/A | Low | Very Low | No | 6-12 Months |  | Low | n |  | Technology; | 03/31/2025 | 12/31/2025 |  | 06/10/2025 | On Hold | NA | NA | No | Simplification; | 1 | Missing |  |  |  |  | 2025-03-11 10:34 | 2025-03-17 11:13 | ABC | NA | [5 empty] | $ 0 | Non Active |  | No | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | On Hold |  |  | This project merge into web app Web & App Backend Upgrade - 3619 (Delivery hub ID) |  |  |  | No |  |  | No
Applied filters: ChangeEntity is BSI