## Deployment Plan RLSE ID
RLSE ID - MEGA ID
# | Start Date | Start Hour | End Date | End Hour | RLSE ID | Task ID | Installation activity description | Environment SIM/SHW/PRO | Assignment Group Snow | Dependencies | Comments
| 2026-03-09 | 9:00 | 2026-03-31 | 18:00 | RLSE1271544 |  | Appian - Security Lending Workflow | PRO | IT Development | N/A
Roll Back
R1
R2
R3
R4
Contact information | [6 empty] | Approval
Contact Name |  |  | Email address |  |  | Cell Phone #
Laura Benevenides |  |  | LBenavides@bpi-gruposantander.com |  |  | +1 305 530 7278
Jesus Largo |  |  | jlargomartinez@bpi-gruposantander.com |  |  | +1 305 530 6541

## Help (hidden)
RLSE00147000 - Data Lake [123]
# | Start Date | Start Hour | End Date | End Hour | RLSE ID | Task ID | Installation activity description | Environment SIM/SHW/PRO | Assignment Group Snow | Dependencies | Comments
1 | 2021-02-24 | 17:00 | 2021-02-24 | 17:30 | RLSE00147000 | RSTK0800000 | Backup 2 Shells(Shell1,Shell2) from the following Server/Path: Server1/root/folder1/ | PRO | SGT_IN_IM_MX_IMPLANTACION | N/A
2 | 2021-02-24 | 18:00 | 2021-02-24 | 18:30 | RLSE00147000 | RSTK0800000 | Deploy 2 Shells(Shell1,Shell2) in the following Server/Path: Server1/root/folder1/ | PRO | SGT_IN_IM_MX_IMPLANTACION | 1899-12-31
3 | 2021-02-24 | 18:30 | 2021-02-24 | 19:00 | RLSE00147000 | RSTK0800001 | Re-start Server1 in order that the change take effect | PRO | SGT_IN_IM_MX_IMPLANTACION | 2
4 | 2021-02-24 | 19:00 | 2021-02-24 | 19:30 |  |  | Validation | PRO | CIO Office | 3
Roll Back
R1 |  |  |  |  | RLSE00147000 | RSTK0800000 | Deploy Backup for the Shell1,Shell2 in the following Server/Path: Server1/root/folder1/ | PRO | SGT_IN_IM_MX_IMPLANTACION | N/A
R2 |  |  |  |  | RLSE00147000 | RSTK0800001 | Re-start Server1 in order that the change take effect | PRO | SGT_IN_IM_MX_IMPLANTACION | R1
R3 | [6 empty] | Validation |  | CIO Office | R2
R4
Contact information
Contact Name |  |  | Email address |  |  | Cell Phone #
Joe Smith |  |  | joe.smith@santander.us |  |  | 16171234567
Business Validator
Technical Vaidator
Example
Example